## START
To use this workbook please enable macros
Do this by clicking the Enable Content option as shown below.
If you have disabled macros, you'll have to close this workbook and then reopen it.
<< Microsoft Office 2016 is required to run this workbook >>
If you require more information, please contact:
Manager (Policy Services)
Phone: +61 7 4631 1578
Email: policy@usq.edu.au

## Policy Activity Log (hidden)
Current Policy Activity 2023 (14 September 2023 - updated weekly)
ENDORSEMENT
Instrument Title | Degree of Change | Dependency/ Trigger | Accountable Officer | Division | Policy Type | Topic | Target Date | Pre-Start | Commencement | Initial Draft | Preliminary Consultation | SI Review | Legal Check Requested | Gazettal | Revise Draft | Academic Board Committee | Academic Board | VCE | Council Sub Committee | Approval Council VC AB | Publication | Notes (Column only viewable by the Policy Advisor)
Contract Management Policy | Development | Audit | DVC (ES) | Enterprise Services | Executive Policy | Contract Management | Q4-Q1 2023 | [5 empty] | Legal Request | [8 empty] | SI Project looking at scoping out audit of this. Dec: Athol/Lisa reviewing updates. Query from R&I: How are they being included? Jacqui now spending 2 days/week on Budget system.
Contract Responsibilities Schedule | Development | Audit | DVC (ES) | Enterprise Services | Schedule | Contract Management | Q4-Q1 2023 | [5 empty] | Legal Request
Contract Risk Management Procedure | Development | Audit | DVC (ES) | Enterprise Services | University Procedure | Contract Management | Q4-Q1 2023 | [5 empty] | Legal Request
Travel Procedure | Major Review | Audit | CPO | Enterprise Services | University Procedure | Travel | Q1 2022 |  |  |  |  | 1. Review - Complete (Feb 2): 2. Consideration of Feedback - In Progress |  | May 27-June 10 |  |  |  | Nov 4
Traveller and Travel Approver Responsibilities Schedule | Development | Audit | CPO | Enterprise Services | Schedule | Travel | Q1 2022 |  |  |  |  | 1. Review - Complete (Feb 2): 2. Consideration of Feedback - In Progress |  | May 27-June 10 |  |  |  | Nov 4
Travel Policy | Major Review | Audit | DVC (ES) | Enterprise Services | Executive Policy | Travel | Q1 2022 |  |  |  |  | 1. Review - Complete (Feb 2): 2. Consideration of Feedback - In Progress |  | May 27-June 10 |  |  |  | Nov 4 |  |  |  | Sept: VC has asked for some contemporary language changes. Membership/points accrual. Oct: Still pending Nov: Still with VC reviewing Neil's feedback. July: With Athol to regroup with VC. Per OM Mar VC
Contract Management Procedure | Development | Audit, Legal | DVC (ES) | Enterprise Services | University Procedure | Contract Management | Q4-Q1 2023 | [5 empty] | Legal Request
Various - Academic Freedom Alignment Changes (Major) | Alignment | Compliance | VC | Vice-Chancellor | Various | Academic Freedom | Q1-Q2 2022 | [14 empty] | Need to manage transition/understand what work is still outstanding.
Continuous Controls Monitoring Policy | Development | Compliance | DVC (ES) | Enterprise Services | Executive Policy | CCM | Q1 2022 |  |  | Collaboration Link Aug 23 2021
Continuous Controls Monitoring Procedure | Development | Compliance | DVC (ES) | Enterprise Services | University Procedure | CCM | Q1 2022 |  |  | Collaboration Link Aug 23 2021
Compliance Policy | Development | Compliance | DVC (ES) | Enterprise Services | Governance Policy | Compliance | Q1-Q2 2022 |  |  |  | Consultation link Aug 23 2021 |  | Legal Request | [8 empty] | Did preliminary Stage 5 in March. Peter has shared his feedback and John is reworking the suite.
Compliance Procedure | Development | Compliance | DVC (ES) | Enterprise Services | University Procedure | Compliance | Q1-Q2 2022 |  |  |  | Consultation link Aug 23 2021 |  | Legal Request
Compliance Schedule | Development | Compliance | DVC (ES) | Enterprise Services | Schedule | Compliance | Q1-Q2 2022 | [5 empty] | Legal Request
Conflict of Interest Procedure | Development | Compliance | DVC (ES) | Vice-Chancellor | University Procedure | Conflict of Interest | Q3-Q4 2022 | [5 empty] | Legal Request | [8 empty] | Requires revision and focus on implementation. Les still seeking support for this, plus implementing PID and Corrupt Conduct. Les needs to resolve some other issues. Put in a Continuous Improvement request to PPSS to revise the process.
Contract Performance Guarantees Procedure | Development | Compliance | CFO | Enterprise Services | University Procedure | Contract Performance Guarantees | Q1 2024 | [5 empty] | Legal Request | [8 empty] | Pretty much tied to Contract Management Suite.
Environmental Management Policy | Major Review | Compliance | ED (FM) | Enterprise Services | Executive Policy | Environmental Management | ON HOLD |  |  |  |  | 18/04/19-24/0419 1. Review-complete 2.Consideration-in progress | [9 empty] | Waiting for new ED (FM) to review. Expecting some revisions (i.e. Alignment with revised leasing suite). July: waiting for sustainability strategy to finalise.
Environmental Management Schedule | Development | Compliance | ED (FM) | Enterprise Services | Schedule | Environmental Management | ON HOLD |  |  |  |  | 18/04/19-24/0419 1. Review-complete 2.Consideration-in progress
Human Research Ethics Procedure | Major Review | Compliance | DVC (R&I) | Research | University Procedure | Human Research Ethics | Q1 - Q2 2024 | [14 empty] | Updates pending government release;
Scholarships, Bursaries and Prizes Policy | Major Review | Compliance | Provost | Academic | Governance Policy | Scholarships, Bursaries & Prizes | ON HOLD | [11 empty] | Chancellor's |  |  | Currently with Dean of students
Superannuation Procedure | Major Review | Compliance | CPO | Enterprise Services | University Procedure | Superannuation | Q4 - Q1 2023 | ? | [13 empty] | Linked to EB in some way
Privacy Policy | Major Review | Compliance | Privacy Officer | Vice-Chancellor | Governance Policy | Privacy | Q3-Q4 2022 | [5 empty] | Legal Request | [8 empty] | August: Les needs to present privacy issues to a management committee. Oct; Not til 2021, may get incorporated in wider info frameworks ES project. June: Les still confirming any changes in responsibility. July: Apparently Les new support person will revise?
Privacy Procedure | Development | Compliance | Privacy Officer | Vice-Chancellor | University Procedure | Privacy | Q3-Q4 2022 |  |  |  |  | Legal Exempt 15/09/2015 - Validate 2021 Review | Legal Request | N/A
Intellectual Property (IP) Policy | Major Review | Compliance, Legal | DVC (R&I) | Research | Governance Policy | Intellectual Property | Q4 2023 |  |  |  | V1 VC & Div Heads (2018) 6/2/19 VCE | V1: 4/07/2016 - complete V2: 11-22/2/19 1. Review-complete 2.Consideration-in prog 3.Confirmation- | Legal Request | V1: Gazettal 24/09-8/10/2015 & SCC 20/07/2016-complete V2: Gazette TBA |  | 2019-05-01 | 4/06/2019 (note) | TBC based on degree of change from gazettal feedback |  |  |  | Had previously gone through Stage 5 (back in 2018). Godrun has spoken with legal and they have agreed to send out to external counsel. Currently working on benchmarking. Then Godrun will bring together stakeholders to get feedback (since many roles have changed). And then we'll get internal agreement on USQ position, then seek external legal advice. Hoping to have internal alignment done Q3/Q4.
National Security Procedure | Development | Compliance, Legal | VC | Vice-Chancellor | University Procedure | National Security | On Hold
Sanctions and Export Controls Procedure | Development | Compliance, Legal | VC | Vice-Chancellor | University Procedure | National Security | On Hold |  |  |  |  | Feb 9-12 2021 | Legal Request | Feb 16-Mar 5 | HOLD | [6 empty] | Rachael amending. Will make changes following VCE alignment/presentation. Why don't I have a sanctions procedure listed here?
Sanctions Compliance Policy | Development | Compliance, Legal | VC | Vice-Chancellor | Governance Policy | National Security | On Hold |  |  |  |  | Feb 9-12 2021 | Legal Request | Feb 16-Mar 5 | HOLD | [6 empty] | March: Pausing so DVC (R&I) can work with Legal to align with feedback. May: JD and SH meeting with Constance Johnson tomorrow re: Foreign Interference. May be some additional procedures as well. Constance will incorporate legal feedback.
Crisis Management Suite | Major Review | Legal | DVC (ES) | Enterprise Services | Executive Policy | Crisis Management | Q3-Q4 2022
Physical Security and Traffic Policy | Development | Legal | ED (FM) | Enterprise Services | Executive Policy | Physical Security | Q2 2022 |  |  |  |  | Latest Stage 5 completed August 5, 2021 | Legal Request | Latest Gazettal completed Feb 2, 2022 | To DVC (ES) Q2 2022 |  |  | VCE Q2 2022 |  |  |  | Jan: VCE feedback requires revisions. Christie White working on it. If no additional gazettal required, could go back to VCE maybe Feb. Revised timing: VCE 14th April, to DVC (ES) 1st April. Target Stage 5 March 1, Gazettal (if needed), no later than March 15. Hoping earlier for Stage 5 if they're doing the whole suite. June 23: Received okay to start the Stage 5. Mar 2: Stage 5 (round 3) commencing, per Nui some procedures no longer progressing. Mar 5: Updated instrument tracker, unwanted procedures archived. May: Revising drafts. Stage 5 May 17. June: Still waiting for Stage 5 to review as of June 3. With Christie White. Sept 2021: Latest stage 5 completed and revied by FM. Should now go on to legal and then gazettal again. Still with legal as of Oct 27.
Alcohol and Drugs on University Sites Procedure | Repeal |  | CPO | Enterprise Services | University Procedure | Alcohol and Drugs | Q1 2023 | [14 empty] | Likely to be repealed. Elliott aligned, Melanie working on it. Waiting to repeal for FM to identify deployment actions to move specific provisions somewhere else. Eryn spoke with Melanie about the FM concerns. (From a safety/security POV the codes of conduct don't cover expectations appropriate\ly) . May require a follow-up meeting. Still planning f/u meeting. With Angelle for approval. In principal approval from Angelle received - seeking feedback from FM and AU about topics covered in current procedure.
Appointments: Modes of Employment Procedure | Minor Review |  | CPO | Enterprise Services | University Procedure | Appointments: Modes of Employment | Q1 2023 | Waiting on EA
Student Academic Misconduct Procedure | Major Review |  | Provost | Academic | University Procedure | Academic Misconduct | Q4 | With DVC AA and AIU | [7 empty] | February | April |  |  |  |  | With DVC (AA)
Coursework Program Teach-out and Transfer Requirements and Exit Qualifications Procedure | Development |  | Provost | Academic | University Procedure | Academic Programs and Courses | Q4 | With Annette | [8 empty] | April |  |  |  |  | Waiting on update from Provost - Leanne to advise
Admissions, Enrolments and Graduations Policy | Development |  | Provost | Academic | Academic Quality Policy | Admissions, Enrolments & Graduation | Q1 2024 |  |  |  | Waiting on Academic Registra Review | [5 empty] | July 26, 2022
Admissions Procedure | Major Review |  | Dir (SAS) | Academic | University Procedure | Admissions, Enrolments & Graduation | Q2 - Q3 2023 |  |  |  | Waiting on Academic Registra Review | [5 empty] | July 26, 2022
Enrolment Procedure | Major Review |  | Provost | Academic | University Procedure | Admissions, Enrolments & Graduation | Q2-Q3 2024 (Rolled in with AEG) |  |  |  | Waiting on Academic Registra Review | [5 empty] | July 26, 2022
Graduations Procedure | Development |  | Provost | Academic | University Procedure | Admissions, Enrolments & Graduation | Q2-Q3 2024 (Rolled in with AEG) |  |  |  | Waiting on Academic Registra Review | [5 empty] | July 26, 2022
Animal Ethics Procedure | Major Review |  | DVC (R&I) | Research | University Procedure | Animal Ethics | Q1 - Q2 2024 | [14 empty] | New procedure to consolidate existing and new info and sit under Research Code of Conduct Policy
Animal Wellbeing and Ethics Policy | Alignment |  | DVC (R&I) | Research | Executive Policy | Animal Ethics | Q1 - Q2 2024 | [14 empty] | Will be repealed and replaced with above.
Unexpected Adverse Event (Animal) Procedure | Alignment |  | DVC (R&I) | Research | University Procedure | Animal Ethics | Q1 - Q2 2024 | [14 empty] | Will be repealed and replaced with above.
Annual Financial Planning (Budget) Procedure | Development |  | DVC (ES) | Enterprise Services | University Procedure | Annual Financial Planning (Budget) | Q3-Q4 2022 | [14 empty] | Comes from PWC Audit. On Hold. Feb 2020: Bumped from Q1-Q2 to Q2. May/June: Leave as is. Mar: Mel has written it. Ready for consultation. July: Budget going through in fall.
Various - EBA Alignment | Alignment |  | CPO | Enterprise Services | Various | EB Alignment | Q1 2023 | Waiting on EA
Student Fees Procedure | Major Review |  | Provost | Academic | University Procedure | Fees | Q4 2023
Assets Policy | Major Review |  | CFO | Enterprise Services | Executive Policy | Assets | Q1 2024 | Possibly combining to one suite | [9 empty] | May 26 2021 |  |  |  | This suite may have ties to the Strategic Asset Management Framework and work FM is doing. Should all align. May be some consolidation. Instrument tracker set up 24/03/2021. targeting May 26 VCE. May: Still pending Stage 5.
Assets Procedure | Major Review |  | CFO | Enterprise Services | University Procedure | Assets | Q1 2024 | Possibly combining to one suite | [9 empty] | May 26 2021
Impairment of Assets Policy | Major Review |  | CFO | Enterprise Services | Executive Policy | Assets | Q1 2024 | Possibly combining to one suite | [9 empty] | May 26 2021
Impairment of Assets Procedure | Major Review |  | CFO | Enterprise Services | University Procedure | Assets | Q1 2024 | Possibly combining to one suite | [9 empty] | May 26 2021
Intangible Assets Policy | Major Review |  | CFO | Enterprise Services | Executive Policy | Assets | Q1 2024 | Possibly combining to one suite | [9 empty] | May 26 2021
Intangible Assets Procedure | Major Review |  | CFO | Enterprise Services | University Procedure | Assets | Q1 2024 | Possibly combining to one suite | [9 empty] | May 26 2021
Inventory Assets Policy | Major Review |  | CFO | Enterprise Services | Executive Policy | Assets | Q1 2024 | Possibly combining to one suite | [9 empty] | May 26 2021
Inventory Assets Procedure | Major Review |  | CFO | Enterprise Services | University Procedure | Assets | Q1 2024 | Possibly combining to one suite | [9 empty] | May 26 2021
Property, Plant and Equipment Policy | Major Review |  | CFO | Enterprise Services | University Procedure | Assets | Q1 2024 | Possibly combining to one suite | [9 empty] | May 26 2021
Property, Plant and Equipment Policy and Procedure | Major Review |  | CFO | Enterprise Services | University Procedure | Assets | Q1 2024 | w | [9 empty] | May 26 2021
Exit Surveys or Interviews Procedure | Repeal |  | CPO | Enterprise Services | University Procedure | Exit interviews | Q1 2021 | ? | [13 empty] | Plan to repeal
Brand Policy | Development |  | PVC (Eng) | Vice-Chancellor | Executive Policy | Brand | Q3-Q4 2022 | Following up on status | [9 empty] | 30 Sept Target |  |  |  | Targeting 30 Sept VCE
Corporate Credit Card Policy | Major Review |  | CFO | Enterprise Services | University Procedure | Corporate Credit Card | Q3-Q4 2023 |  |  |  | Consultation link sent August 23 2021 | [6 empty] | TBD |  |  |  | Dec: Pending Rob's review. Mar; Cass has raised with Rob. July: Cass said it had fallen off the radar but may be back on.
Corporate Credit Card Procedure | Major Review |  | CFO | Enterprise Services | University Procedure | Corporate Credit Card | Q3-Q4 2023 |  |  |  | Consultation link sent August 23 2021 | [6 empty] | TBD
Costing and Pricing (General) Procedure | Major Review |  | CFO | Enterprise Services | University Procedure | Costing and Pricing | Q3-Q4 2023 |  |  |  |  | Review completed March 2019, now revising.
Costing and Pricing (Policy) | Major Review |  | CFO | Enterprise Services | Executive Policy | Costing and Pricing | Q3-Q4 2023 |  |  |  |  | Review completed March 2019, now revising. | [9 empty] | 2018/2019: Drafted, had Stage 5, then on hold. Drafter: Mel Reimann Feb 2020: Timing pushed to Q2. May: Still hoping for Q2, but delayed due to budget. June: Pushed to Q3 Mel away until start of Jan, so minor likely end Q1, major in Q2.
Costing and Pricing (Research) Procedure | Major Review |  | CFO | Enterprise Services | University Procedure | Costing and Pricing | Q1 2024 |  |  |  |  | Review completed March 2019, now revising.
Costing and Pricing Policy | Major Review |  | DVC (ES) | Enterprise Services | Executive Policy | Costing and Pricing | Q4 2022 |  |  |  |  | Review completed March 2019, now revising. | [5 empty] | Q1 2019
Costing and Pricing Policy | Minor Review |  | DVC (ES) | Enterprise Services | Executive Policy | Costing and Pricing | Q4 2022 | [14 empty] | May try to combine with Major.
Internal User Charging and Cost Recovery Procedure | Major Review |  | DVC (ES) | Enterprise Services | University Procedure | Costing and Pricing | Q4 2022
Council Conflict of Interest |  |  | TBD | Vice-Chancellor |  | Council COI | Q2-Q3 2022
Council Election Policy | Major Review |  | VC | Vice-Chancellor | Governance Policy | Council Elections | Q2-Q3 2022
Council Electrion Procedure | Major Review |  | VC | Vice-Chancellor | University Procedure | Council Elections | Q2-Q3 2022
Cyber Security Procedure | Development |  | DVC (ES) | Enterprise Services | University Procedure | Cyber Security | ON HOLD | [14 empty] | HOLD pending DIT Strategy
Flexible Working Arrangements Procedure | Major Review |  | CPO | Enterprise Services | University Procedure | Flexible Arrangements | Q1 2023 | Waiting on EA
Drones Policy | Development |  | ED (FM) | Enterprise Services | Executive Policy | Drone | Q3-Q4 2022 | [14 empty] | Currently considering whether this should be a guideline or a policy suite.
Drones Procedure | Development |  | ED (FM) | Enterprise Services | University Procedure | Drone | Q3-Q4 2022
Working from Another Location Procedure | Major Review |  | CPO | Enterprise Services | University Procedure | Flexible Arrangements | Q1 2023 | Waiting on EA
Fee Setting Procedure | Repeal |  | Provost | Academic | University Procedure | Fees | Q4 2023
Refund of Student Fees Policy and Procedure (Will become procedure only) | Repeal |  | Provost | Academic | University Procedure | Fees | Q4 2023
Employee Health and Wellbeing Procedure | Major Review |  | TBD | Enterprise Services |  | Employee Health and Well Being | Q2 2022 | [14 empty] | Melanie going to follow up with Ann on that.
Endowment Policy | Development |  | VC | Vice-Chancellor | Governance Policy | Endowment | Q2 2022
Enterprise Risk Management Policy | Development |  | DVC (ES) | Enterprise Services | Governance Policy | Enterprise Risk Management | Q4 2022
Enterprise Risk Management Procedure | Development |  | DVC (ES) | Enterprise Services | University Procedure | Enterprise Risk Management | Q4 2022
Risk Appetite Statements Schedule | Development |  | DVC (ES) | Enterprise Services | Schedule | Enterprise Risk Management | Q4 2022
Risk Management Policy | Alignment |  | Dir (AS) | Enterprise Services | Governance Policy | Enterprise Risk Management | Q4 2022 | [5 empty] | Legal Request | Apr |  |  |  | May/June | Audit & Risk - July; Chancellor's Sept | Council - Oct 18 |  | Anticipate Stage 5 around July 2020. July: Just about ready! August: Waiting for Michael's Input. Sept: Still with Michael. Oct/Nov: No Change. Dec: Have DVC (ES) Feedback. Need to check with OM re: how frequently DVC (ES) wants to review (i.e. Before, after stage 5). Dec: Confirmed with OM that DVC (ES) Doesn't need to see it til after gazettal. July: Now aligned, Peter is doing a further consultation. January: Stage 5 about to start, then on to Legal March: Stage 5 completed, back for revision Mar 16: John working through feedback from Stage 5. April Gazettal, May VCE, July Audit & Risk, Sept 23 Chancellor's, Oct 18 Council. Need much quicker gazettal Apr: Still pending Peter's feedback; May gazettal, then see above.
Risk Management Procedure | Alignment |  | Dir (AS) | Enterprise Services | University Procedure | Enterprise Risk Management | Q4 2022 | [5 empty] | Legal Request | Apr |  |  |  | May/June | Audit & Risk - July; Chancellor's Sept | Council - Oct 18 |  | See above.
Built Environment Procedure | Development |  | ED (FM) | Enterprise Services | University Procedure | Estate Management | Q3-Q4 2022 |  |  |  |  | 25/2-5/4/19 1. Review-complete 2.Consideration-complete 3.Confirmation-complete |  | 23/4/19-31/5/19 | With Campus Services
Domestic Animal Management Procedure | Development |  | ED (FM) | Enterprise Services | University Procedure | Estate Management | Q3-Q4 2022 |  |  |  |  | 25/2-5/4/19 1. Review-complete 2.Consideration-complete 3.Confirmation-complete |  | 23/4/19-31/5/19 | With Campus Services
Estates Management Policy | Development |  | ED (FM) | Enterprise Services | Executive Policy | Estate Management | Q3-Q4 2022 |  |  |  |  | 25/2-5/4/19 1. Review-complete 2.Consideration-complete 3.Confirmation-complete |  | 23/4/19-31/5/19 | With Campus Services | [6 empty] | Holding for ED (FM) review.
Flag Protocols Procedure | Development |  | ED (FM) | Enterprise Services | University Procedure | Estate Management | Q3-Q4 2022 |  |  |  |  | 25/2-5/4/19 1. Review-complete 2.Consideration-complete 3.Confirmation-complete |  | 23/4/19-31/5/19 | With Campus Services
Furniture Procedure | Development |  | ED (FM) | Enterprise Services | University Procedure | Estate Management | Q3-Q4 2022 |  |  |  |  | 25/2-5/4/19 1. Review-complete 2.Consideration-complete 3.Confirmation-complete |  | 23/4/19-31/5/19 | With Campus Services
Land and Property Management Procedure | Development |  | ED (FM) | Enterprise Services | University Procedure | Estate Management | Q3-Q4 2022 |  |  |  |  | 25/2-5/4/19 1. Review-complete 2.Consideration-complete 3.Confirmation-complete |  | 23/4/19-31/5/19 | With Campus Services
Space Management Procedure | Major Review |  | ED (FM) | Enterprise Services | University Procedure | Estate Management | Q2-Q3 2022 |  |  |  |  | 25/2-5/4/19 1. Review-complete 2.Consideration-complete 3.Confirmation-complete |  | 23/4/19-31/5/19 | With Campus Services | [6 empty] | Currently benchmarking. Depends on campus master plan.
Use and Hire of Facilities Procedure | Major Review |  | ED (FM) | Enterprise Services | University Procedure | Estate Management | Q3-Q4 2022 |  |  |  |  | 25/2-5/4/19 1. Review-complete 2.Consideration-complete 3.Confirmation-complete |  | 23/4/19-31/5/19 | With Campus Services
Events Policy | Development |  | VC | Vice-Chancellor | Executive Policy | Events | Q3-Q4 2021 | [14 empty] | Was on hold at end of Dec 2019. Drafter: Sian Benson Spoke Feb 7th, partially drafted but not getting much focus anytime soon due to volume of events to manage. Now thinking June. Sept: Going back and revising again. Oct: Laureen will chase up Sian to get an update. Possible link in with HR - could incorporate management of Alcohol at events
Events Procedure | Development |  | VC | Vice-Chancellor | University Procedure | Events | Q3-Q4 2021
Inclusive Terminology (Alignment Changes to Library) | Minor Review |  | CPO | Enterprise Services | Executive Policy | Inclusive Terminology | Q4-Q1 2022 | [14 empty] | Pending outcome of Athena Swann application, etc in February 2020. March 2020: No progress April/May 2020: No announcement/no news. June: may or may not include the RAP August/Sept: nothing new Athena Swan Bronze award was successful - so may be some resources.
Expenditure Policy | Major Review |  | CFO | Enterprise Services | Executive Policy | Expenditure | Q1 2024 | [14 empty] | Likely to be memo for major with only minor change
Expenditure Procedure | Major Review |  | CFO | Enterprise Services | University Procedure | Expenditure | Q1 2024 | [14 empty] | Likely to be memo for major with only minor change
Fees Policy | Major Review |  | Dir (SAS) | Academic | Executive Policy | Fees | Q3-Q4 2022 | [14 empty] | Development proposal approved, but not much else done. Feb 2020 - timing pushed out until 2021. Still drafting. Elliot to come back with details on timing. May: Pending due to staff absence.
Student Debt Management Procedure | Repeal |  | Provost | Academic | University Procedure | Fees | Q4 2023
Student Discrimination Bullying Harassment and Sexual Misconduct: Prevention and Response Procedure | Development |  | Provost | Academic | University Procedure | Prevention of Discrimintation, Bullying and Harassment | Q4 2023 | legal office |  |  |  |  | Legal Request
Employee Harassment, Discrimination and Bullying Procedure | Major Review |  | CPO | Enterprise Services | University Procedure | Prevention of Discrimintation, Bullying and Harassment | Q1-Q2 2023 | Waiting on EA |  |  |  |  | Legal Request
Fraud and Corruption Management Policy | Major Review |  | VC | Vice-Chancellor | Governance Policy | Fraud and Corruption | Q2 2022 | [5 empty] | Legal Request | [8 empty] | Dec: Plan finalisation waiting for Corrupt Conduct Resolution suite approval as a dependency. Jan: Council approved PIT and Corrupt Conduct Resolution. Once Plan approved, can move on to policies/procedures. J Feb: Instrument tracker started mid 2020 but never finished. Sent to John again Feb 10 so he can revise and we can get set-up. Les Mitchell has provided feedback on the Fraud & Corruption Control Plan. Updated: Instrument Tracker finalised and sent to Lisa Cornish for review. Set up. Mar: John will do more drafting. uly: The Plan is with Peter who is seeking review from Michael.
Fraud and Corruption Management Procedure | Major Review |  | DVC (ES) | Enterprise Services | University Procedure | Fraud and Corruption | Q2 2022 | [5 empty] | Legal Request
Gift Acceptance Policy | Development |  | VC | Vice-Chancellor | Governance Policy | Gift Acceptance | Q1 2022-Q2 2022 | [14 empty] | Kicked off with Stephen Holden and Romaine Carpenter in late May 2021
Gift Acceptance Procedure | Development |  | PVC (ENG) | Vice-Chancellor | University Procedure | Gift Acceptance | Q2-Q3 2022 | Following up on status | [13 empty] | Kicked off with Stephen Holden and Romaine Carpenter in late May 2021
Gifts and Benefits Procedure | Minor Review |  | CFO | Enterprise Services | University Procedure | Gifts & Benefits | Q3-Q4 2023
Development of New Scholarships, Bursaries and Prizes Procedure | Development |  | Provost | Academic | University Procedure | Scholarships, Bursaries & Prizes | ON HOLD | [14 empty] | Currently with Dean of students
Commercialisation of USQ IP Procedure | Development |  | DVC (R&I) | Research | University Procedure | Intellectual Property | Q1 - Q2 2024 | [5 empty] | Legal Request
Copyright Procedure | Development |  | DVC (R&I) | Research | University Procedure | Intellectual Property | Q3 - Q4 2024 | [5 empty] | Legal Request
Hospitality and Entertainment Policy | Development |  | CFO | Enterprise Services | Executive Policy | Hospitality and Entertainment | Q1 2024 |  |  |  |  | 25/3-12/4/19 1. Review-complete 2.Consideration-in progress |  | 09/12/19-06/01/20 |  |  |  | Nov 4 |  |  |  | VC had revisions, likely requires another Stage 5. Re-drafting.
Hospitality and Entertainment Procedure | Development |  | CFO | Enterprise Services | University Procedure | Hospitality and Entertainment | Q1 2024 |  |  |  |  | 25/3-12/4/19 1. Review-complete 2.Consideration-in progress |  | 09/12/19-06/01/20 |  |  |  | Nov 4
Peer Review Procedure | Development |  | DVC (R&I) | Research | University Procedure | Peer Review | TBD | [8 empty] | 2022-10-12 | 2022-11-15 |  |  |  |  | May link with Research COI.
Employee Sexual Harm Prevention and Response Procedure | Development |  | CPO | Enterprise Services | University Procedure | Prevention of Discrimintation, Bullying and Harassment | Q4 - Q1 2023 | Dependant on student's one |  |  |  |  | Legal Request
Information Systems Financial Management Procedure | Alignment |  | CFO | Enterprise Services | University Procedure | Information Systems Financial Management Procedure | TBD | Potentially to be superceded | [13 empty] | Possible this will be repeal
Integrated Planning and Performance Policy | Development |  | DVC (ES) | Enterprise Services | Governance Policy | Integrated Planning and Performance | Q4 2022
Integrated Planning and Performance Procedure | Development |  | DVC (ES) | Enterprise Services | University Procedure | Integrated Planning and Performance | Q4 2022
Minimum Project Standards Schedule - Capital Projects | Development |  | DVC (ES) | Enterprise Services | Schedule | Integrated Planning and Performance | Q4 2022
Minimum Project Standards Schedule - Technology Projects | Development |  | DVC (ES) | Enterprise Services | Schedule | Integrated Planning and Performance | Q4 2022
Research Code of Conduct: Management of Potential Breaches Procedure | Major Review |  | DVC (R&I) | Research | University Procedure | Research Code of Conduct: Management of Potential Breaches | TBD | [8 empty] | June 22 2022 | July 26 2022
Research Conflicts Interest Procedure | Development |  | DVC (R&I) | Research | University Procedure | Research Conflict of Interest | TBD | [8 empty] | Oct 12, 2022 | Nov 15, 2022 |  |  |  |  | Pending further discussion between R&I and Assurance Services (March 2020) No change (April 2020). Les and Julianna to chat after COI discussed at audit & risk. Also still waiting for CCC report which is expected to have some recommendations. July: Per Sarah, CCC checking base in Nov, so will want to show some progress. Research Fraud Guide from CCC released. May end up linked with Peer Review. Feb: The need is questionable - JD considering it some more. June: Definitely want it, in framework.
Interest Bearing Funds Policy | Minor Review |  | CFO | Enterprise Services | Executive Policy | Interest Bearing Funds | Q1 2024
Interest Bearing Funds Procedure | Minor Review |  | CFO | Enterprise Services | University Procedure | Interest Bearing Funds | Q1 2024
Investments and Cash Management Policy | Minor Review |  | VC | Vice-Chancellor | Governance Policy | Investments and Cash Management | Q3-Q4 2022
Investments and Cash Management Procedure | Minor Review |  | VC | Vice-Chancellor | University Procedure | Investments and Cash Management | Q3-Q4 2022
Indigenous Commonwealth Scholarships Schedule | Development |  | Provost | Academic | Schedule | Scholarships, Bursaries & Prizes | ON HOLD | [14 empty] | Currently with Dean of students
Management of Scholarships, Bursaries and Prizes Procedure | Development |  | Provost | Academic | University Procedure | Scholarships, Bursaries & Prizes | ON HOLD | [14 empty] | Currently with Dean of students
Student Communication Policy | Major Review |  | Provost | Academic | Executive Policy | Student Communication | Q4 2023 | [14 empty] | Currently with Dean of students
Student Communication Procedure | Repeal |  | Provost | Academic | University Procedure | Student Communication | Q4 2023 | [14 empty] | Currently with Dean of students
Student General Misconduct Procedure | Major Review |  | Provost | Academic | University Procedure | Student Conduct | Q3 - Q4 2023 | legal office |  |  |  |  | Legal Request | [8 empty] | With Linda Bird for feedbacak.
Mobile Device and Service Policy | Major Review |  | ED (ICT) | Enterprise Services | Executive Policy | Mobile Device & Service | Q4 2021-Q1 2022 |  |  |  | Consultation link provided June 1
Mobile Device and Service Procedure | Major Review |  | ED (ICT) | Enterprise Services | University Procedure | Mobile Device & Service | Q4 2021-Q1 2022 |  |  |  | Consultation link provided June 1
Motor Vehicle Policy | Major Review |  | ED (FM) | Enterprise Services | Executive Policy | Motor Vehicle | Q2-Q3 2022 |  |  |  |  | 11/3-5/4/19 1. Review-complete 2.Consideration-Complete 3.Confirmation- Complete |  | 23/4/19-31/5/19 |  |  |  | Presented at Dec 11 VCE, revising based on feedback. |  |  |  | Olivia has provided required changes to team and they are revising. June: Turns out that wasn't the latest feedback and they're still seeking it. Oct: Team making minor changes, then back to DVC ES office and onto VCE and VC.
Motor Vehicle Procedure | Major Review |  | ED (FM) | Enterprise Services | University Procedure | Motor Vehicle | Q2-Q3 2022 |  |  |  |  | 11/3-5/4/19 1. Review-complete 2.Consideration-Complete 3.Confirmation- Complete |  | 23/4/19-31/5/19 |  |  |  | Presented at Dec 11 VCE, revising based on feedback.
Vehicle Selection Schedule | Development |  | ED (FM) | Enterprise Services | Schedule | Motor Vehicle | Q2-Q3 2022 |  |  |  |  | 11/3-5/4/19 1. Review-complete 2.Consideration-Complete 3.Confirmation- Complete |  | 23/4/19-31/5/19 |  |  |  | Presented at Dec 11 VCE, revising based on feedback.
Organisational Section Reviews Policy | Major Review |  | DVC (ES) | Enterprise Services | Executive Policy | Organisation Section Review | Q1-Q2 2022 |  |  |  | HOLD | [10 empty] | Developed to the point of preliminary consultation then on hold for future use of this function.
Organisational Section Reviews Procedure | Development |  | DVC (ES) | Enterprise Services | University Procedure | Organisation Section Review | Q1-Q2 2022 |  |  |  | HOLD
Research Data and Primary Materials Management Procedure | Major Review |  | DVC (R&I) | Research | University Procedure | Research Data & Primary Materials Management | Q3 - Q4 2023 | [14 empty] | Procedure work may end up minor. Racheal Chester is leading.
Parking and Traffic Management Procedure | Development |  | ED (FM) | Enterprise Services | University Procedure | Physical Security | Q2 2022 |  |  |  |  | Latest Stage 5 completed August 5, 2021 | Legal Request | Latest Gazettal completed Feb 2, 2022 | To DVC (ES) Q2 2022 |  |  | VCE Q2 2022
Physical Security Equipment and Infrastructure Procedure | Development |  | ED (FM) | Enterprise Services | University Procedure | Physical Security | Q2 2022 |  |  |  |  | Latest Stage 5 completed August 5, 2021 | Legal Request | Latest Gazettal completed Feb 2, 2022 | To DVC (ES) Q2 2022 |  |  | VCE Q2 2022
Physical Security Procedure | Development |  | ED (FM) | Enterprise Services | University Procedure | Physical Security | Q2 2022 |  |  |  |  | Latest Stage 5 completed August 5, 2021 | Legal Request | Latest Gazettal completed Feb 2, 2022 | To DVC (ES) Q2 2022 |  |  | VCE Q2 2022
Policy and Procedure Framework | Major Review |  | VC | Vice-Chancellor | Governance Policy | Policy and Procedure Framework | Q1-Q2 2022 | [5 empty] | Legal Request | [8 empty] | Policy Health Check taking place in 2021. Phase 1 (Apr-May); Phase 2 (June-Aug); Phase 3: Sept/Oct Phase 4: Nov/Dec
Portable and Attractive Assets Policy | Minor Review |  | CFO | Enterprise Services | Executive Policy | Portable and Attractive Assets | Q1 2024 |  |  |  | Minor | [10 empty] | 2019: Drafter: Joe Guerini Joe is on secondment, so Abby leading that project. Expect movement by end October. 2020: Per Feb, still no movement here. Stalled.
Portable and Attractive Assets Procedure | Minor Review |  | CFO | Enterprise Services | Executive Policy | Portable and Attractive Assets | Q1 2024 |  |  |  | Minor
Student General Misconduct Procedure Penalty Schedule | Major Review |  | Provost | Academic | Schedule | Student Conduct | Q3 - Q4 2023 | legal office |  |  |  |  | Legal Request | [8 empty] | With Linda Bird for feedbacak.
Prevention of Discrimintation, Bullying and Harassment Procedure | Major Review |  | VC | Vice-Chancellor | University Procedure | Prevention of Discrimintation, Bullying and Harassment | Q3-Q4 2022 | [5 empty] | Legal Request
Student Critical Incident Procedure | Development |  | Provost | Academic | University Procedure | Student Critical Incident | ON HOLD? | [5 empty] | Legal Request | [8 empty] | Stalled out
Procurement Procedure | Minor Review |  | CFO | Enterprise Services | University Procedure | Procurement | Q1 2024 | [14 empty] | With Athol.
Procurement Threshold Authorisation Schedule | Minor Review |  | CFO | Enterprise Services | Schedule | Procurement | Q1 2024
Procurement Procedure | Major Review |  | CFO | Enterprise Services | University Procedure | Procurement - Uni Market | Q1 2024
Student Wellbeing Policy | Major Review |  | Provost | Academic | Executive Policy | Student Well Being | ON HOLD |  |  |  | S&C Exec 29/11/18 | 14/11-28/11/18 |  | 17/12/18-25/1/19 |  |  |  | HOLDING as at 21/8/2019 |  |  |  | Unclear where Policy is tracking Deb Sutton's absence (Feb 2020). Leanne to follow up with Christie White. Pending details on Deb Sutton as resource (March 2020
Public Interest Disclosure Policy | Minor Review |  | VC | Vice-Chancellor | Governance Policy | Public Interest Disclosure | Q2-Q3 2022
Public Interest Disclosure Procedure | Minor Review |  | Dir (I&PC) | Vice-Chancellor | University Procedure | Public Interest Disclosure | Q2-Q3 2022 | [14 empty] | Need some amendments; Les also working on training with PP;
Records and Information Management Policy | Major Review |  | DVC (ES) | Enterprise Services | Executive Policy | Records and Information | Q1-Q2 2022 | [5 empty] | Legal Request | [8 empty] | Discussed with Sheree and Kaye - looking to make some revisions. Kirryn Austin attended, this is one that will likely be looked at by their ICT working party. Strong likelihood of having one policy (Records and Information Management) and multiple procedures.
Records and Information Management Procedure | Major Review |  | DVC (ES) | Enterprise Services | University Procedure | Records and Information | Q1-Q2 2022 | [5 empty] | Legal Request
Research Management Procedure | Development |  | DVC (R&I) | Research | University Procedure | Research Management | Q1 2024 | [8 empty] | Oct 12, 2022 | Nov 15, 2022
Higher Degree Research Program Designs and Structures Procedure | Development |  | DVC (R&I) | Research | University Procedure | Research Program Designs and Structure | Q4 2023 | [8 empty] | Oct 12, 2022 | Nov 15, 2022
Research Structures Procedure (will rename Research Institutes and Centres Procedure) | Major Review |  | DVC (R&I) | Research | University Procedure | Research Structure | Q1 - Q2 2024 | [8 empty] | Aug 17, 2022 | Sept 20, 2022
Australian Commonwealth Government Research Training Program (RTP) Scholarship Policy Schedule | Major Review |  | DVC (R&I) | Research | Schedule | RTP Scholarship Policy Schedule | Q1-Q2 2023 | [8 empty] | 2022-10-12 | 2022-11-15 | 2022-06-08 |  |  | 2023-04-01
Research Active Procedure | Development |  | DVC (R&I) | Research | University Procedure | Research Active | Q4 2022 |  |  |  | Not complete yet. | May 3- May 9 - first round, expect to do again. |  |  |  | Oct 12, 2022 | Nov 15, 2022 |  |  |  | 2022-10-10
HDR Research Supervision Procedure | Major Review |  | DVC (R&I) | Research | University Procedure | HDR Supervision and Student Support | Q4 2022 |  |  |  |  | Dec 16, 20021 |  | Mar 23-Apr 7 |  | August 17, 2022 | 2022-09-20 |  |  |  | 2022-10-10
HDR Student Scholarship Procedure | Development |  | DVC (R&I) | Research | University Procedure | HDR Student Scholarshp | Q1-Q2 2023 | [8 empty] | October 12, 2022 | 2022-11-01 |  |  |  | 2023-04-01
Right to Information Policy | Major Review |  | Privacy Officer | Enterprise Services | Executive Policy | Right to Information | Q1-Q2 2022 | [5 empty] | Legal Request | [8 empty] | Switched over from EIMS to Les. Les unsure if this is his responsibility. Les putting forward a concept to VCE, but that has been delayed.
Right to Information Procedure | Major Review |  | Privacy Officer | Enterprise Services | University Procedure | Right to Information | Q1-Q2 2022 | [5 empty] | Legal Request
HDR Student Admissions and Enrolments Procedure | Development |  | DVC (R&I) | Research | University Procedure | HDR Student Admissions and Enrolments Procedure | Q4 2022 |  |  |  |  | Mar 3, 2022 |  | Mar 23-Apr 7 |  | August 17, 2022 | 2022-09-20 |  |  |  | 2022-10-10
RPA Suite | Development |  | DVC (ES) | Enterprise Services | Various | RPA | Q1-Q2 2022 | [14 empty] | Likely DVC (ES) A/O; Director PPSS (R/O). Dates per Fiona Margetts. 60 Day Pilot - Apr-June
Students with a Disability and Carer Support Procedure | Major Review |  | Provost | Academic | University Procedure | Students with a Disability | ON HOLD |  |  |  |  | Latest Stage 5 completed Nov 4, 2021 | Legal Request | [8 empty] | Per Elliot, had been sitting and waiting for inputs from Executive Dean HES. June 2021: Still waiting for guidance on inherent requirements.
Students with a Disability and Carer Support and Adjustments Schedule | Major Review |  | Provost | Academic | Schedule | Students with a Disability | ON HOLD |  |  |  |  | Latest Stage 5 completed Nov 4, 2021 | Legal Request | [8 empty] | Per Elliot, had been sitting and waiting for inputs from Executive Dean HES. June 2021: Still waiting for guidance on inherent requirements.
Under 18 Students Policy (Former Under 18 International Students Policy) | Major Review |  | Provost | Academic | Executive Policy | Under 18 | Q1 - Q2 2024 | [14 empty] | International Student Care Framework - dependent on appointment to International Admissions Manager role. Per FM, this framework referenced in Under 18 International Student Policy and need to make sure that there isn't a conflict. Stalled for ages.
Academic Dress Schedule | Minor Review |  | PVC (S) | Academic | Schedule | Award Eligibility | [14 empty] | 2021-02-18
Academic Freedom Policy | Development | Compliance | VC | Vice-Chancellor | Governance Policy | Academic Freedom | [5 empty] | Review - Completed Sept 25; Consideration: Complete |  | Oct 6-Oct 14 *Exemption for 9 day gazettal as per Director (PPSS) |  |  | 2017-11-01 |  | 2019-11-01 | 2014-12-01 | 2020-12-16
Social Media Procedure | Development |  | PVC (ENG) | Vice-Chancellor | University Procedure | Social Media | TBA | [5 empty] | Legal Request | [8 empty] | Requires considerable consultation with relation to Academic Freedom, Interantional, Students, Privacy, etc.
Social Media Policy | Development |  | PVC (ENG) | Vice-Chancellor |  | Social Media | TBA
Academic Integrity Policy | Major Review |  | DVC (A) | Academic | Academic Quality Policy | Academic Integrity | [5 empty] | Review: Complete Oct 12; Consideration: Oct 13 -19 |  | Oct 21-4 Nov |  | Oct 29 | Nov 17 | Nov 4 |  | AB Nov17 | 2020-12-09
Sponsorships Procedure | Development |  | PVC (ENG) | Vice-Chancellor | University Procedure | Sponsorships | ON HOLD |  |  |  |  | Review: Sept 18-Sept 25; Consideration: Sept 25+ | Legal Request | Nov 9-21 |  |  |  | Jan 20, 2021 - Further Revision and subsequent VCE required. |  |  | 2022-12-01 | Placed on hold pending Audit and potentially revised framework with new PVC (Eng)
Work Integrated Learning Placements and Projects Procedure | Development |  | Provost | Academic | University Procedure | Work Integarted Learning | Q4 - Q1 2024 |  |  | With TEQSA2024 project team | [11 empty] | Further discussions to happen with Provost
Work Integrated Learning Policy | Development |  | Provost | Academic | Academic Quality Policy | Work Integrated Learning | Q3 - Q4 2023 |  |  | With TEQSA2024 project team | [11 empty] | Further discussions to happen with Provost
Residential Schools Procedure | Major Review |  | Provost | Academic | University Procedure |  | Q4 - Q1 2024 | [14 empty] | Waiting on commencement of Dean (Learning and Teaching Futures)
Microcredentials Policy | Development |  | Provost | Academic | Academic Quality Policy | Short course /micro that are seen more as professional development | ON HOLD | AQU | [13 empty] | Under Director Microcredentialing unit
Microcredentials and Professional Development Procedure | Development |  | Provost | Academic | University Procedure |  | ON HOLD | AQU | [13 empty] | Under Director Microcredentialing unit
Coursework Dual Awards and Joint Degrees Procedure | Development |  | Provost | Academic | University Procedure | Education Partnerships | Q3 - Q4 2023 | [5 empty] | Legal Request |  |  | Jan 2021 | Feb 2021 | Jan/Feb 2021 |  | VC Feb 2021 |  | Go to Academic Program around Jan/Feb. Stage 5 before Dec 17. Endorsed by AB subject o legal review, still sitting there.
English Language Profiency Requirements Schedule | Major Review |  | Provost | Academic | Schedule |  | Q3 - Q4 2023 | [14 empty] | To replace the minor review version that is currently active.
Determining equivalence of professional experience to Academic Qualifications Procedure | Development |  | Provost | Academic | University Procedure | Equivalence to Academic Qualifications | Q3-Q4 2023 | [14 empty] | Audit outcome
Workwear Procedure | Repeal |  | CPO | Enterprise Services | University Procedure | Workwear | Q1 2022 | ? | [13 empty] | Possible repeal
Harassment and Discrimination Complaint Resolution for Students Procedure | Repeal |  | Provost | Academic | University Procedure | Prevention of Discrimintation, Bullying and Harassment | Q2 - Q3 2023 | Confirm merge/repeal to Procedure below |  |  |  |  | Legal Request
Student Defence Force Reservists Support Policy and Procedure | Repeal |  | Provost | Academic |  |  | Q1 - Q2 2024 | [14 empty] | Broader support piece coming
Use of the Univerity Seal Policy | Major Review |  | VC | Vice-Chancellor | Governance Policy | University Seal | Q2-Q3 2022 | [14 empty] | Mark believes still fit for purpose, will validate with Council.
Use of the University Seal Procedure | Minor Review |  | VC | Vice-Chancellor | University Procedure | University Seal | Q2-Q3 2022 | [14 empty] | Mark has minor review version, will take through Chancellor's/Council.
Incident and Hazard Reporting and Investigation Procedure | Major Review |  | DVC (ES) | Enterprise Services | University Procedure | WH&S | Q2-Q3 2022 |  |  |  |  | Nov 4-5 2021 | [9 empty] | Nov: Spoke with Caitlin - she's going to map everything out and come back to me; Minor updates to Policy, keeping one procedure, repeal rest and replace with Manuals. Two down! Two major revisions: Targeting May 1 Stage 5 Revised to beginning June Stage 5.; June 23 VCE - Incident Reporting; Risk later. (10 Nov VCE - mid Sept Stage 5 ; Prelim Consult early to Mid August). KH Followed up with CI to check timing. Work Health & Safety Procedures and Safety Manuals Procedure - Minor
Safety Investigation Reporting Schedule | Major Review |  | DVC (ES) | Enterprise Services | Schedule | WH&S | Q2-Q3 2022 |  |  |  |  | Nov 4-5 2021 | [9 empty] | Nov: Spoke with Caitlin - she's going to map everything out and come back to me; Minor updates to Policy, keeping one procedure, repeal rest and replace with Manuals. Two down! Two major revisions: Targeting May 1 Stage 5 Revised to beginning June Stage 5.; June 23 VCE - Incident Reporting; Risk later. (10 Nov VCE - mid Sept Stage 5 ; Prelim Consult early to Mid August). KH Followed up with CI to check timing. Work Health & Safety Procedures and Safety Manuals Procedure - Minor
Work Health and Safety Risk Management Procedure | Major Review |  | DVC (ES) | Enterprise Services | University Procedure | WH&S | Q2-Q3 2022 |  |  |  |  | Sept 2021 | [5 empty] | 2021-11-10
Recruitment & Selection Procedure | Minor Review |  | CPO | Enterprise Services | University Procedure | Probity/Recruitment & Selection | Q1 2023 | ? | [12 empty] | 2022-11-17 | Based on need to be clear what due diligence is required to ascertain that a job candidate is eligible to work in Australia prior to scheduling an interview. No progress through 2020. May be held off due to EB. Feb 15: Moved up a quarter as per T. O'Neil.
Other Leave Type Schedule | Minor Review |  | CPO | Enterprise Services | Schedule | Other Leave Type | Q1 2022 | [13 empty] | 2022-08-01
Course Specifications Requirements Schedule | Minor Review |  | Provost | Academic | Schedule |  | Q1 2023 | [9 empty] | 2023-02-01 |  |  |  | 2023-03-01
Employee Domestic and Family Violence Support Procedure | Alignment |  | CPO | Enterprise Services | University Procedure | Domestic Violence | Q1-Q2 2022 | [13 empty] | 2022-08-01 | With CPO and heading to the VC
Academic Development and Outside Studies Processes Schedule | Repeal |  | CPO | Enterprise Services | Schedule | Academic Development and Promotion | Q2 2022 | [13 empty] | 2022-08-01
Q3 - Q4 2023 | Major Review |  | Provost | Academic | Executive Policy | Library | Q2 - Q3 2023 | [13 empty] | 2023-03-01 | Library staff to run
Q3 - Q4 2023 | Major Review |  | Provost | Academic | University Procedure | Library | Q2 - Q3 2023 | [13 empty] | 2023-03-01
Class of Honours Standard Schedule | Major Review |  | DVC (AA) | Academic | Schedule |  | Q4 2023
Q3 - Q4 2023 | Major Review |  | Provost | Academic | University Procedure | Library | Q2 - Q3 2023 | [13 empty] | 2023-03-01
Parental Leave Policy | Development |  |  | Enterprise Services |  |  |  | ?
Employee Excellence Awards | Minor Review |  |  | Enterprise Services
Q3 - Q4 2023 | Major Review |  | Provost | Academic | University Procedure | Library | Q2 - Q3 2023 | [13 empty] | 2023-03-01 | Note: This is of relevance to the Engagement Portfolio
Cotutelle and Joint PhD Procedure | Major Review |  | Provost | Academic | University Procedure | Joint PHD/Cotutelle (via R&I) | Q1 2023 | [5 empty] | Legal Request | [7 empty] | 2023-03-01 | Edits proposed, doing consultation. Feedback from research committee. Some discussion from Academic about what policy this should sit under (i.e. Education Partnerships). Still sorting out where this should sit. Sarah is discussing with John.
Graduate Attributes Policy | Major Review |  | Provost | Academic | Academic Quality Policy | Graduate Attributes | Q1 2023 |  | Minor approval from Provost | [11 empty] | 2023-03-01 | Came up for review cycle and determined that change was required - going for approval
Academic Development and Outside Studies Program Procedure | Major Review |  | CPO | Enterprise Services | University Procedure | Academic Development and Promotion | Q2 2022 | [13 empty] | 2022-08-01
Academic Integrity Procedure | Major Review |  | DVC (A) | Academic | University Procedure | Academic Integrity | [5 empty] | Review: Complete Oct 12; Consideration: Oct 13 -19 |  | Oct 21-4 Nov |  | Oct 29 | Nov 17 | Nov 4 |  | VC | 2021-02-22
Academic Integrity Procedure | Minor Review |  | DVC (A) | Academic | University Procedure | Penalty Update | [14 empty] | 2020-08-13
Academic Integrity Procedure Penalty Schedule | Major Review |  | DVC (A) | Academic | Schedule | Academic Integrity | [5 empty] | Review: Complete Oct 12; Consideration: Oct 13 -19 |  | Oct 21-4 Nov |  | Oct 29 | Nov 17 | Nov 4 |  | VC | 2021-02-22
Academic Integrity Procedure Penalty Schedule | Minor Review |  | DVC (A) | Academic | University Procedure | Penalty Update | [14 empty] | 2020-08-13
Academic Programs and Courses Quality Policy | Major Review |  | DVC (A) | Academic | Academic Quality Policy | Academic Programs and Courses | Q1 2022 | [12 empty] | 2022-02-22 | 2002-04-13
Academic Standing, Progression and Exclusion Procedure | Minor Review |  | DVC (A) | Academic | University Procedure | Penalty Update | [14 empty] | 2020-08-13
Admissions Procedure | Minor Review |  | PVC (S) | Academic | University Procedure | Admissions - Cancellations | [14 empty] | 2021-03-11
ADOSP Procedure - Major Review (renamed Program for Excellence in Research and Teaching Procedure) |  |  | CPO | Enterprise Services | University Procedure | [5 empty] | SCC 26/10-9/11/18 | 30/10/18-12/11/18 |  | n/a |  |  |  | 2018-12-05 |  | A/VC 12/3/19 | 2019-03-14
Assessment and Grades Roles and Resopnsibilities schedule | Development |  | DVC (A) | Academic | Schedule | Assessment | Q1 2022 | [13 empty] | Feb 14, 2022
Assessment Hurdles Schedule |  |  | SDVC | Academic | Schedule | [6 empty] | 8/11-6/12/17 | [5 empty] | 2017-12-13 |  | 2018-01-17 | 2022-04-06
Assessment Hurdles Schedule |  |  | DVC (A) | Academic | Schedule | [14 empty] | 2018-06-28 | 2022-04-06
Assessment Patterns Schedule | Development |  | DVC (A) | Academic | Schedule | Assessment | Q1 2022 | [13 empty] | Feb 14, 2022
Assessment Patterns Schedule | Minor Review |  | DVC (A) | Academic | Schedule | Assessment | Q2 2022 | [13 empty] | 2022-03-31
Assessment Policy | Major Review |  | DVC (A) | Academic | Academic Quality Policy | Assessment | Q4 2021-Q1 2022 |  |  |  | DVC A - Approved to publish with procedure |  |  | #1 Sept 9-20 #2 18-29 Nov |  |  |  | Jan 22, 2020 | Education Quality Committee Jan 23. | 2018-02-01 | Feb 14, 2022 | Phase implementation? Including policy?
Assessment Procedure | Development |  | DVC (A) | Academic | University Procedure | Assessment | Q1 2022 |  |  |  |  | Sept 24-Sept 29 |  |  |  | Oct 29 | 2017-11-01 | Nov 4 |  | VC | Feb 14, 2022
Assessment Types Schedule | Development |  | DVC (A) | Academic | Schedule | Assessment | Q1 2022 |  |  |  |  | Sept 24-25 |  |  |  | Oct 29 | 2017-11-01 | Nov 4 |  | VC | Feb 14, 2022
Assessment Types Schedule | Minor Review |  | DVC (A) | Academic | Schedule | Assessment | Q2 2022 | [13 empty] | 2022-04-06
Australian Commonwealth Government Research Training Progam (RTP) Scholarship Policy Schedule (subordinate to Scholarships Bursaries and Prizes Policy) |  | Compliance | DVC (R&I) | Research | Executive Policy, Schedule | [5 empty] | VCC Endorsed 9/08/2017 | In parallel with VC initial briefing | [7 empty] | VC - 22/12/1/7 | 2018-01-02
Authorship Procedure (Major Review) |  | Audit | DVC (R&I) | Research | University Procedure | [10 empty] | 2020-01-22 | 2020-02-18 |  |  | AB 18 Feb 2020 | 2020-02-18
Award Eligibility Specific Criteria Schedule | Minor Review |  | PVC (S) | Academic | Schedule | USQ Upskill/Undergraduate Certificates | [13 empty] | DVC A | 2020-07-10
Award Eligibility Specific Criteria Schedule | Major Review |  | PVC (S) | Academic | Schedule | Award Eligibility - Repeal with C&E | Q3-Q4 2021 | [13 empty] | 2021-08-13 | Repeal with publication of Credit & Exemption (July 12, 2021) Mar: Likely to repeal schedule as part of Credit & Exemption. Policy will be repealed under AEG> C&E Approved for implementation for 12 July 2021.
BioSafety Procedure | Development | Audit, Compliance | DVC (ES) | Enterprise Services | University Procedure | Biosafety | [5 empty] | 2021-02-15 |  |  | Due to DVC (ES) by 19 Feb |  |  | 31 Mar |  | 2021-03-31 | 2021-04-07
Biosafety Standard Work Practices Schedule | Development | Audit, Compliance | DVC (ES) | Enterprise Services | Schedule | Biosafety | [11 empty] | 31 Mar |  | 2021-03-31 | 2021-04-07
Borrowing Policy | Major Review |  | CFO | Enterprise Services | Executive Policy | Borrowings | [5 empty] | Review Completed: Sept 25-20; Consideration: Complete |  | Oct 21-4 Nov |  |  |  | Dec 2 |  | VC Dec 2 | 2010-12-01
Borrowings Procedure | Major Review |  | CFO | Enterprise Services | University Procedure | Borrowings | [5 empty] | Review Completed: Sept 25-20; Consideration: Complete |  | Oct 21-4 Nov |  |  |  | Dec 2 |  | VC Dec 2 | 2020-12-10
Business Continuity and Crisis Management Procedure |  |  | ED (FM) | Enterprise Services | University Procedure | [12 empty] | 2018-02-21 |  | 2018-03-01 | 2018-03-23
Business Continuity Policy |  |  | ED (FM) | Enterprise Services | Executive Policy | [5 empty] | Div Heads 8/8/17 | Commenced 5/09/17 Legal Exempt |  | Gazette Exempt |  |  |  | 2018-02-21 |  | 2018-03-01 | 2018-03-23
Class of Honours Standard Schedule | Minor Review |  | DVC (A) | Academic | Schedule | PC Grades | [13 empty] | DVC A | 2020-07-10
Complaint Management Policy | Development | Audit | VC | Vice-Chancellor | Governance Policy | Complaints |  |  |  |  | VCE 20/3/19 (initial consult) VCE - Corrupt Conduct focus 15/5/19 TBC | [9 empty] | 2010-12-01
Complaints About the Vice-Chancellor Policy |  |  | Chancellor | Vice-Chancellor | Governance Policy | Crime & Corruption Commission Approval of Draft - Confirmed 5/6/19 |  |  |  |  | VCE 29/5/2019 | 29/5/2019 - Expedited Process to meet CCC timelines. |  | ED (CMS exemption 20/5/19) |  |  |  | 2019-05-29 | Chancellor's 13/6/19 (endorse) | 2019-07-08 | 2019-07-08
Conflict of Interest Policy |  | Audit | VC | Vice-Chancellor | Governance Policy | [5 empty] | VCC Consult - 4/05/2016 VCC Consult - 13/12/17 VCE Consult - 15/8/18 ESD Managers - 10/4/19 |  |  | Exempt (ED CMS 12/4/19) | n/a |  |  | 2019-05-15 | Chancellor's; 13/6/19 - Sent back for revisions, resent 15/8/19 | Approved 09/09/2019 | 2019-09-19
Corrupt Conduct Resolution Policy | Development | Audit | Dir (I&PC) | Vice-Chancellor | Governance Policy | Corrupt Conduct | [5 empty] | Partial Review Completed: Sept 22-Sept 25; Pending Deployment Plan. |  | Exemption: Oct 12, 2020 | VCE asekd for some additional consultation run in parallel. |  |  | Oct 21 | Nov 19 | Dec 14 | 2021-01-27
Corrupt Conduct Resolution Procedure | Development | Audit, Compliance | Dir (I&PC) | Vice-Chancellor | University Procedure | Corrupt Conduct | [5 empty] | Partial Review Completed: Sept 22-Sept 25; Pending Deployment Plan. |  | Exemption: Oct 12, 2020 | VCE asekd for some additional consultation run in parallel. |  |  | Oct 21 | Nov 19 | Dec 21 | 2021-01-27
Council Delegations Schedule (Minor) |  |  | Uni Secretary | Vice-Chancellor | Schedule | [13 empty] | Apr 16 2020 | May 11 2020 | 2020-05-15
Council Delegations Schedule (SDVC delegation - dependent on related DVC (S&C) considerations) |  |  | Uni Secretary | Vice-Chancellor | [6 empty] | at 28/2/18 | [8 empty] | 2016-03-29 | 2018-04-06
Council Election Policy/Procedure |  | Compliance | VC | Vice-Chancellor | Executive Policy, University Procedure | [5 empty] | VCE 16/5/18 | 16/5-1/6/18 |  | Gazette 21-31/5/18 |  |  |  |  | Chancellor's 14/6/8 | 2018-07-09 | 2018-07-20
Council Remuneration Schedule | Minor Review |  | VC | Vice-Chancellor | Schedule | Council Remuneration | Q3 2021 | [12 empty] | 2021-08-31 | 2021-09-06
Course Numbering and Naming Schedule | Minor Review |  | DVC (A) | Academic | Schedule | USQ Upskill/Undergraduate Certificates | [13 empty] | DVC A | 2020-07-10
Coursework Curriculum Design and Structure Procedure | Development |  | DVC (A) | Academic | University Procedure | Curriculum Design | Q3 2021 |  |  |  |  | February 2021 |  |  |  |  | June 8 |  |  |  | Sept 10, 2021
Coursework Curriculum Design and Structure Schedule | Development |  | DVC (A) | Academic | Schedule | Curriculum Design | Q3 2021 |  |  |  |  | February 2021 |  |  |  |  | June 8 |  |  |  | Sept 10, 2021
Coursework Delivery Procedure (formerly Education Partnership Procedure) | Development |  | PVC (S) | Academic | University Procedure | Education Partnerships | [5 empty] | Review Compelted Oct 9; Consderation: Active |  | Oct 21-4 Nov |  |  | Nov 17 | Nov 18 |  | VC Jan 20 | 2021-02-10
Coursework Quality Assurance – Evaluation Procedure | Development |  | DVC (A) | Academic | University Procedure | Academic Programs and Courses | Q1 2022 | [9 empty] | Feb 22 2022 |  |  |  | 2022-04-13 | Per Lyn, going to AB in Feb, so need Jan committees and Stage 5 in December. Unsure if other instruments included.
Credit and Exemption Procedure | Minor Review |  | PVC (S) | Academic | University Procedure | USQ Upskill/Undergraduate Certificates | [13 empty] | DVC A | 2020-07-10
Credit and Exemption Procedure (Major Revision to Pending Version) | Major Review |  | PVC (S) | Academic | University Procedure | Credit and Exemption | Q1 2022 | [13 empty] | 2022-04-13
Credit and Exemption Procedure (Pending Version) | Major Review |  | DVC (A) | Academic | University Procedure | Credit and Exemption | Q2 2022 |  |  |  |  | Review: Oct 27-Nov 10; Now Revising. Second wave review completed Nov 23. |  |  |  | 21 Jan Academic Program Committee; Returning Mar 18; | 2020-04-01 | Dec 2 |  |  | 2022-04-05 | May: Approved! Publication July 12, 2021. Publication to be delayed to S1 pending AB dates.
Credit and Expemption Procedure | Minor Review |  |  | Academic | University Procedure | Credit and Exemption | Q2 2023 | [13 empty] | 2022-05-12
Crisis Management Policy |  | Legal | ED (FM) | Enterprise Services | Executive Policy | [8 empty] | Exempt | Post VCC 17/05/2017 Legal Review of indemnity clause r'd 13/11/17 |  |  | 17/05/2017 (complete) 21/2/18 |  | 2018-03-01 | 2018-03-23
Curriculum Design Policy | Development |  | DVC (A) | Academic | Academic Quality Policy | Curriculum Design | Q3 2021 | [9 empty] | June 8 |  |  |  | Sept 10, 2021 | Program committee 24 June, AB 27 July. Approved by AB, pending VC Procedure approval.
Delegations Policy | Minor Review |  | VC | Vice-Chancellor | Governance Policy | Financial Delegations | [13 empty] | Council July 13 2020 | 2020-07-16
Education Partnership Policy | Major Review |  | PVC (S) | Academic | Academic Quality Policy | Education Partnerships | [5 empty] | Review Compelted Oct 9; Consderation: Active |  | Oct 21-4 Nov |  |  | Nov 17 | Nov 18 |  | AB Nov 17 | 2021-02-10
Electronic Signatures Policy - Development |  |  | DVC (ES) | Enterprise Services | Executive Policy | [6 empty] | March 2020 |  | Exempt per Acting Director PPSSS (12/03/2020) |  |  |  | 2020-04-01 |  |  | 2020-04-01
Electronic Signatures Procedure - Development |  |  | DVC (ES) | Enterprise Services | University Procedure | [6 empty] | March 2020 | [5 empty] | 2020-04-01 |  |  | 2020-04-01
Electronic Signatures Procedure - Minor Review |  |  | DVC (ES) | Enterprise Services | University Procedure | [5 empty] | Drafting | [9 empty] | 2020-04-22
English Language Profiency Requirements Schedule | Minor Review |  | DVC (A) | Academic | Schedule | English Language Requirements | [14 empty] | 2021-02-22
English Language Requirements Schedule | Minor Review |  | PVC (S) | Academic | Schedule | English Language Requirements | [14 empty] | 2020-07-01
English Language Requirements Schedule - Review Minor |  |  | PVC (S) | Academic | Schedule | [6 empty] | n/a |  | n/a | n/a | n/a | na/ | n/a | n/a | 20/08/2018 by A/DVC (S&C) | 2019-02-25
Enrolment Procedure | Minor Review |  | PVC (S) | Academic | University Procedure | Admissions - Cancellations | [14 empty] | 2021-03-11
Enrolment Procedure | Minor Review |  | DVC (A) | Academic | University Procedure | Enrolment Procedure | Q1 2022 | [13 empty] | Feb 24, 2022
Enterprise Bargaining Suite (incl 70 minor reviews) |  | Compliance | DVC (ES) | Enterprise Services | Executive Policy, 8 x Schedule, 15 x University Procedure | [6 empty] | 8/8-3/9/18 |  | n/a - separate EB process |  | n/a | n/a | 2018-12-05 | n/a | Fair Work Aust approved 27/3/19 (submitted 10/10/18) VC approved 12/12/18 | 2019-04-09
Estate Naming Policy | Major Review |  | VC | Vice-Chancellor | Governance Policy | Estate Naming | Q3 2021 | [6 empty] | Exemption secured |  |  |  |  | 29th July | 2021-08-23 | 2021-08-25
Estate Naming Procedure | Minor Review |  | VC | Vice-Chancellor | University Procedure | Estate Naming | Q3 2021 | [11 empty] | 29th July | 2021-08-23 | 2021-08-25
Evaluation of Teaching, Courses & Programs Policy | Alignment |  | DVC (A) | Academic | Academic Quality Policy | Academic Programs and Courses | Q1 2022 | [13 empty] | Repeal - 13/04/2022 | Repeal
Evaluation of Teaching, Courses & Programs Procedure | Alignment |  | DVC (A) | Academic | Academic Quality Policy | Academic Programs and Courses | Q1 2022 | [13 empty] | Repeal - 13/04/2022 | Repeal
Financial Delegations Schedule | Major Review |  | DVC (ES) | Enterprise Services | Schedule | Financial Delegations | [13 empty] | Council July 13 2020 | 2020-07-16
Financial Delegations Schedule |  | Audit | CFO | Enterprise Services | Schedule | [14 empty] | 2018-02-16 | 2018-02-19
Financial Delegations Schedule (VC research contract signing limit change) |  |  | CFO | Enterprise Services | Schedule | [14 empty] | 2018-05-14 | 2018-05-24
Financial Reporting Policy | Minor Review |  | CFO | Enterprise Services | Executive Policy | Financial Reporting | [14 empty] | 2020-12-15
Financial Reporting Procedure | Minor Review |  | CFO | Enterprise Services | University Procedure | Financial Reporting | [14 empty] | 2020-12-15
Formal Examinations Procedure | Minor Review |  | PVC (S) | Academic | University Procedure | USQ Upskill/Undergraduate Certificates | [13 empty] | DVC A | 2020-07-10
Formal Examinations Procedure - Major Review Stage 1 |  | Audit | PVC (S) | Academic | University Procedure | [6 empty] | pre-publication |  |  |  | n/a | n/a | n/a VC approved 13/2/18 | n/a | 2018-02-13 | 2018-02-23
Fraud and Corruption Management (Interim) Policy - Major Review |  | Compliance | VC | Vice-Chancellor | [6 empty] | VCE 20/3/19 (initial consult) | 1. Review - Complete 2. Consideraiton - active |  | Exempt |  |  |  | Dec 11 2019 | Pending formal minutes was endorsed at Feb 13, 2020 meeting | Mar 9, 2020 council meeting. | 2020-03-20
Fraud and Corruption Management (Interim) Procedure - Major Review |  | Compliance | DVC (ES) | Enterprise Services | University Procedure | [5 empty] | VCE 20/3/19 (initial consult) | 1. Review - Complete 2. Consideraiton - active |  | Exempt |  |  |  | Dec 11 2019 | Pending formal minutes was endorsed at Feb 13, 2020 meeting | Mar 9, 2020 council meeting. | 2020-03-20
General Ledger Journal Procedure | Minor Review |  | CFO | Enterprise Services | University Procedure | General Ledger | [14 empty] | 2020-12-15
Gifts and Benefits Procedure |  | Compliance | DVC (ES) | Enterprise Services | University Procedure | [6 empty] | 12-1/3/19 |  | n/a |  |  |  | 2019-05-01 |  | 2019-05-14 | 2019-05-21
Grade Point Average (GPA) Calculation Schedule (Minor Review) |  |  | DVC (A) | Academic | Schedule | [5 empty] | DVC A - Drafting | [9 empty] | 2020-04-28
Grades Procedure | Development |  | DVC (A) | Academic | University Procedure | Assessment | Q1 2022 |  |  |  |  | Sept 24-25 |  |  |  | Oct 29 | 2017-11-01 | Nov 4 |  | VC | Feb 14, 2022
Grades Procedure | Minor Review |  | VC | Academic | University Procedure | Assessment | Q1 2022 | [13 empty] | 2022-04-06
Grades Schedules (Minor Review) |  |  | DVC (A) | Academic | Schedule | [5 empty] | DVC A - Drafting | [9 empty] | 2020-04-28
Graduate Research School policy & procedure alignments |  |  | DVC (R&I) | Research | [16 empty] | 2019-02-11
HDR Confirmation of Candidature | Major Review |  | DVC (R&I) | Research | Schedule | HDR Confirmation of Candidature | Q1 2022 |  |  |  |  | Dec 15, 2021 |  |  |  | March 16, 2022 | April 19 2022 |  |  |  | 2022-04-01 | 14/11/19 - Looking at a few changes, including dropping panel from Chair Plus 2 to Chair plus 1. Will check with FM regarding minor status. Feb 2020: I looked over the proposed changes and had some questions. Pending response from Julianna. Was discussed at research committee in March and JD thinks there may have been some feedback/follow-up actions. May: No update at this time, pending follow-up with Alyce June: Charlotte was checking in with Peter. Alyce to f/u. July: Sarah will f/u with Alyce to see if any change. August: Same Oct: Sarah to send to me to confirm if still minor. Nov: Sarah has double-checked with key items of consultation then come back to me. June 2021: Still pending results of confirmation. July: Expect confirmation for minor. October: Unsure if still minor, additional changes, Cassie/Sarah to send through. Nov: Still mionr, but wanting to run by Research Committee in Jan.
HDR Student Policy | Development |  | DVC (R&I) | Research | Academic Quality Policy | HDR Student | Q3-Q4 2021 |  |  |  |  | Mostly complete (July 7) |  | July 16-July 30 |  | RC- 18 Aug | 2021-09-21 |  |  | AB 21/09/2021 | 2021-10-26 | Broader consultation; In Gazettal currently, on track for VCE. Stage 5 to Kelly by end of June 2021 Gazettal – for 2 weeks (finished by end of July – put in for Gazett by July 19) 4 August 2021 for VCE (if needed) Research Committee for endorsement – 18 August 2021 (papers due) Academic Board for approval – 21 September (just pending confirmation) Publish
HDR Student Progress Review Schedule | Development |  | DVC (R&I) | Research | Schedule | HDR Student Progress Schedule | Q2 2022 | [8 empty] | March 16, 2022 | April 19 2022 |  |  |  | 2022-04-01 | Note: Separate instrument tracker as Schedule will follow procedure. Endorsed, but going back again due to formatting and some text adjustments.
HDR Student Progression Procedure | Development |  | TBD | Research | University Procedure | HDR Student Progression | Q3 2021 |  |  |  |  | Apr 12-14 |  |  |  | RC - 23 June | 2021-07-27 | 2021-05-26 |  | VC Aug 8, 2021 | 2021-10-07 | Approved - ON HOLD as of Aug 9 in terms of publication
HDR Supervision and Student Support Procedure | Minor Review |  | DVC (R&I) | Research | University Procedure | HDR Supervision | [14 empty] | 2020-07-22
HDR Thesis Presentation Schedule /Phd by Publication | Major Review |  | DVC (R&I) | Research | Academic Quality Policy | HDR Thesis/Phd by Publication | Q2 2022 |  |  |  |  | Dec 16, 2021 |  |  |  | March 16, 2022 | April 19 2022 |  |  |  | 2022-04-01 | June: Still Stalled due to resource scarcity. July/August: Presume same. Sept: Same Oct: Same [12:46 pm] Kelly Hamlet Okay, if that's the case, let's say your draft is done by end June. You take July to do preliminary consultation and get me to do a Stage 5. Let's assume that can happen by end July. No gazettal required, so you could go to VCE for July 7 or July 21. Then Then Research Committee in August, Academic board in September, then the VC approves. So, I'd say if they have the templates readay for end September they're laughing. Mar: Cassie's Tier 2; Cassie to do instrument tracker; Targeting october completion. \ May: Get instrument tracker. June: Instrument tracker complete. July: Cassie drafting for preliminary consultation.
High Risk Biological Materials and Activities Schedule | Development | Audit, Compliance | DVC (ES) | Enterprise Services | Schedule | Biosafety | [5 empty] | 2021-02-15 | [5 empty] | 31 Mar |  | 2021-03-31 | 2021-04-07
Higher Doctorates Policy and Procedure | Major Review |  | DVC (R&I) | Research | Academic Quality Policy | Higher Doctorates | Q1 2022 | [9 empty] | 2021-11-01 |  |  |  | Mar 2, 2022 | Jan/Feb/March 2020: : DVC A was aligned, but now R&I is questioning whether needed - April need to hear from Rachel re: whether we are repealing or not. May: There are parts the DVC R&I wants to keep, so Sarah and Rachel working with him to understand what he actually wants. Becoming major, so will run by AB July 27 to okay repeal of policy, and seek okay to send from RC in August to VC for approval. Then board for noting. Sarah to talk to Grant. June: Still pending DVC feedback July: Same Oct: No Change Nov: Set up minor review version. Jan: Sarah following up with John Bell w/o Jan 18 *TEQSA impact as per Leanne, need movement by Sept Mar: Sarah to put the edits into the very old existing minor review. Needs to be done before AB meeting 27th July. May: July 27th. June: Converting to procedure. Benchmarking. July: Currently in preliminary consultation. Oct: Went to repeal the policy and replace with procedure. The repeal is okay but the content got stalled at AB, it was pushed back to VCE. VCE has happened. Went to RC Oct 2021 and a 1:1 with the VC. Now going back to document tabled at AB.
Historical Archives Collection Policy/Procedure |  |  | Dir (PPSS) | Enterprise Services | Executive Policy, University Procedure | [6 empty] | Complete 31/5/18 |  | 12-26/6/18 |  |  |  | 2018-10-31 |  | 2018-11-06 | 2018-11-13
HR Delegation Schedule |  |  | CPO | Enterprise Services | Schedule | [12 empty] | 2019-04-17 |  |  | 2019-04-26
Leasing Policy | Major Review |  | CFO | Enterprise Services | Executive Policy | Leasing | [5 empty] | Review Completed: Sept 25-20; Consideration: Complete |  | Oct 21-4 Nov |  |  |  | Dec 2 |  | VC Dec 2 | 2020-12-11
Leasing Procedure | Major Review |  | CFO | Enterprise Services | University Procedure | Leasing | [5 empty] | Review Completed: Sept 25-20; Consideration: Complete |  | Oct 21-4 Nov |  |  |  | Dec 2 |  | VC Dec 2 | 2020-12-11
Legal Services Policy - Development |  | Audit | Dir (LS) | Enterprise Services | Executive Policy | [6 empty] | 11-25/1/19 1. Review- 2.Consideration- 3.Confirmation- |  | Exempt per DVC (ES) (19/24PL) | [5 empty] | 2020-04-14 | 2020-05-18
Legal Services Procedure - Development |  | Audit | Dir (LS) | Enterprise Services | University Procedure | [6 empty] | 11-25/1/19 1. Review- 2.Consideration- 3.Confirmation- |  | Exempt per DVC (ES) (19/24PL) | [5 empty] | 2020-04-14 | 2020-05-18
Liabilities Policy | Minor Review |  | CFO | Enterprise Services | Executive Policy | Liabilities | [14 empty] | 2021-01-12
Liabilities Procedure | Minor Review |  | CFO | Enterprise Services | University Procedure | Liabilities | [14 empty] | 2021-01-12
Liabilities Procedure | Minor Review |  | CFO | Enterprise Services | University Procedure | Liabilities | [14 empty] | 2021-01-12
Library Policy Suite |  |  | DVC (A) | Academic | 2 x Executive Policy, 2 x University Procedure | [6 empty] | 4/9-26/11/18 |  | 22/10-5/11/18 |  | n/a | 19/02/2019 (noting) | Post AB 19/2/19 | n/a | VC 25/3/19 | 2019-04-04
Medals and Awards With Distinction Schedule - Minor |  |  | PVC (S) | Academic | Schedule | [11 empty] | 2020-06-09 |  |  | 2020-06-21 | 2020-06-25
Multiple with SDVC internal role/responsibility reference - DVC (S&C) |  |  | PVC (S) | Academic | [6 empty] | at 28/2/18 | [8 empty] | 2018-03-29 | 2018-04-06
Multiple with SDVC internal role/responsibility reference with AO=ED (ES) |  |  | DVC (ES) | Enterprise Services | [6 empty] | at 28/2/18 | [8 empty] | 2018-03-02 | 2018-04-19
Multiple with SDVC internal role/responsibility reference with AO=ED (F&PC) defunct AO to be addressed through EB processes |  |  | DVC (ES) | Enterprise Services | [6 empty] | at 28/2/18 | [6 empty] | 2018-12-05 |  | Submitted to Fair Work Aust 10/10/18 VC approved 12/12/18 | 2019-04-09
Multiple with VCC reference (change to VCE) |  |  | VC | Vice-Chancellor | [15 empty] | 2018-02-06 | 2018-02-19
OS-Help Procedure | Major Review |  | PVC (S) | Academic | University Procedure | OS-Help | DONE UPDATE |  |  |  |  | 1/06/2020 1. Review - Complete 2. Consideration - Active | [8 empty] | 2021-08-03 | August: Briefing, then on to VCE, then to VC for approval including repeal of Policy. Sept: Gone to Committee. January: Waiting for international prior to writing a paper to repeal it. July: With DVC A for approval to repeal. February: Looking at including with other repeals. Elliot. May: No news - see what happens with storeroom mailroom. June: Send Elliott the draft.
Policy and Procedure Framework - Academic Quality focussed major review |  | Audit | VC | Vice-Chancellor | Governance Policy | [8 empty] | 17/-31/1/19 |  | n/a | 2019-02-19 | 2019-01-23 | Chancellors 14/2/19 | 2019-03-25 | 2019-04-26
Prevention of Discrimintation, Bullying and Harassment and Sexual Misconduct Policy | Development |  | VC | Vice-Chancellor | Governance Policy | Prevention of Discrimintation, Bullying and Harassment | Q3-Q4 2021 | [6 empty] | Nov 9-25 |  |  | 16th Nov 2021 | Oct 27 2021 | 18th Nov 2021 | 13th Dec 2021 | Dec 16, 2021 | Combined effort, ESD & Academic, with Governance implications. Replaces SASH Suite work. Make sure Gabriella knows that the ones that is a combined policy and procedure has to split and lose policy.
Procurement Policy | Major Review | Audit, Compliance | CFO | Enterprise Services | Executive Policy | Procurement | [5 empty] | Feb/Marh 2020 |  | 3 March 2020-17 March 2020 | March 2020 |  |  | Apr 2 2020 |  |  | 2020-09-28
Procurement Procedure | Major Review | Audit, Compliance | CFO | Enterprise Services | University Procedure | Procurement | [5 empty] | Feb/Marh 2020 |  | 3 March 2020-17 March 2020 | March 2020 |  |  | Apr 2 2020 |  |  | 2020-09-28
Procurement Procedure | Minor Review |  | CFO | Enterprise Services | University Procedure | Procurement Phase 1 | [5 empty] | August 3, 2020 | [8 empty] | 2020-08-03
Procurement Threshold Authorisation Schedule | Major Review | Audit, Compliance | DVC (ES) | Enterprise Services | Schedule | Procurement | [5 empty] | Feb/Marh 2020 |  | 3 March 2020-17 March 2020 | March 2020 |  |  | Apr 2 2020 |  |  | 2020-09-28
Program Change, Suspension and Discontinuation Approval Procedure | Development |  | DVC (A) | Academic | University Procedure | Academic Programs and Courses | Q1 2022 | [13 empty] | 2022-04-13
Program Accreditation Procedure | Major Review |  | DVC (A) | Academic | University Procedure | Academic Programs and Courses | Q2 | [13 empty] | 2022-05-04
Program Accreditation Procedure (to replace Program Accreditation and Review Procedure - to be repealed) |  | Compliance | DVC (A) | Academic | 2 x Schedule, University Procedure | [5 empty] | 22/10-2/11/18 | 14/5/19-17/5/19 1. Review - Complete. 2. Considation - Complete 3. Confirmation - Complete |  | n/a |  |  | 20/11/2018 Complete 16/4/19 post L&T Taskforce input | 2019-06-28 |  | 2019-06-28 | 2019-07-29
Program Nomenclature Schedule | Minor Review |  | DVC (A) | Academic | Schedule | USQ Upskill/Undergraduate Certificates | [13 empty] | DVC A | 2020-07-10
Program Quality Assurance and Re-accreditation Procedure | Development |  | DVC (A) | Academic | University Procedure | Academic Programs and Courses | Q1 2022 | [13 empty] | 2022-04-13
Promotion to Level B for Academic Employees Procedur | Minor Review |  | CPO | Enterprise Services | University Procedure | Promotion to Level B | [14 empty] | 2021-01-11
Promotion to Level B for Academic Employees Procedure | Major Review |  | CPO | Enterprise Services | University Procedure | Academic Development and Promotion | Q4 2021 | [13 empty] | Dec 7 2021
Promotion to Levels C, D, and E for Academic Employees Procedure (Major Review) | Major Review |  | CPO | Enterprise Services | University Procedure | Academic Promotion | Q1 2022 |  |  |  |  | April 1, 2022 | [7 empty] | 2022-04-13 | 2022-04-20
Promotion to Levels C, D, and E for Academic Employees Procedure (Major Review) |  |  | CPO | Enterprise Services | University Procedure | [15 empty] | 2020-04-22
Public Interest Disclosure Policy | Major Review | Compliance | VC | Vice-Chancellor | Governance Policy | Public Interest Disclosure | [5 empty] | As part of Drafting Support |  | Exemption: August 12, 2020 |  |  |  | Oct 21 | Nov 19 | Dec 21 | 2021-01-27
Public Interest Disclosure Procedure | Development | Compliance | Dir (I&PC) | Vice-Chancellor | University Procedure | Public Interest Disclosure | [5 empty] | As part of Drafting Support |  | Exemption: August 12, 2020 |  |  |  | Oct 21 | Nov 19 | Dec 14 | 2021-01-27
Qualities of a Graduate Policy - Major Review (renamed Graduate Attributes Policy) |  | Compliance | DVC (A) | Academic | Academic Quality Policy, University Procedure | [6 empty] | 18-24/7/18 |  | Gazettal - 27/08/18 - 10/9/18 |  | TBA | 2019-09-24 | 14/11/2018 complete 28/06/2019 by Acting VC Karen Nelson |  |  | 2019-09-24
Records Management Governance Policy and Procedure - Review Major (renamed Records Information Management Governance Policy/Procedure) |  | Compliance | Dir (PPSS) | Enterprise Services | Governance Policy, University Procedure | [6 empty] | Complete 31/5/18 |  | 12-26/6/18 |  | n/a | n/a | 2018-12-05 | n/a | VC 12/12/18 | 2018-12-18
Research Code of Conduct Policy - major review (Note 6); |  | Audit | DVC (R&I) | Research | Governance Policy | [5 empty] | VCE 20/2/19 | 11-1/3/19 |  | 4-15/3/19 (Deployment Plan in parallel) |  | Research C'ttee 20/03/2019 | 16/04/2019 (noting) | 3/4/19 (endorse) | Chancellor's 11/4/19 (endorse) | 2019-05-13 | 2019-07-01
Research Code of Conduct: Investigation of Potential Breaches Procedure (Note 6); Student Research Misconduct Penalty Schedule (Major Review) |  | Compliance | DVC (R&I) | Research | Schedule, University Procedure | [6 empty] | 7/5/19-9/5/19 (Procedure); 13/5/19-24/5/19 Schedule |  | SCC (in parallel with Research Committee 1/5/19) |  | 2019-05-01 | 2019-06-04 | 15/5/19? |  | 2019-06-24 | 2019-07-01
Research Data and Primary Materials Management Procedure |  | Audit | DVC (R&I) | Research | University Procedure | [10 empty] | 2020-01-22 | 2020-02-18 |  |  | AB 18 Feb 2020 | 2020-02-18
Research Data Management and Indigenous Data Governance Schedule | Development |  | DVC (R&I) | Research | Schedule | Research Data & Primary Materials Management | Q4 2021 | [8 empty] | Oct 13, 2021 | Nov 15, 2011 | 2021-10-27 |  |  | Feb 3 2022
Research Policy | Development |  | DVC (R&I) | Research | Academic Quality Policy | Research | Q3-Q4 2021 |  |  |  |  | Aug 24, 2021 - Aug 27 |  | Sept 6-Sept 17 |  | RC Oct | Nov 16 2021' |  |  |  | Jan 27 2022 | Research Committee for consultation – 18 August Broader consultation Stage 5 with Kelly Hamlet Gazettal for 2 weeks VCE – 29 September 2021 Research Committee for endorsement – 13 October 2021 Academic Board for approval – 16 November AB Sent to VC for approval (Tracey Tyres via email) Publish - As of July 2021: Drafting/reviewing.
Research Structures Procedure (replacing Centres of Research and Development Procedure) |  |  | DVC (R&I) | Research | University Procedure | [5 empty] | VCC (out of session) | 18-15/2/18 | [5 empty] | 2018-01-24 |  | 2018-02-27 | 2018-02-28
Revenue Policy/Procedure |  | Compliance | CFO | Enterprise Services | Executive Policy, University Procedure | [6 empty] | 16/5-30/5/19 1. Review-complete 2.Consideration-complete 3. Confirmation - complete |  | Exemption from ED CMS approved 18/6/19 |  |  |  | July 10, 2019 |  | VC July 23, 2019 | 2019-07-24
SDVC accountability reassignment |  | Compliance | SDVC | Academic | 7 x Academic Quality Policy, 14 x Schedule, 6 x University Procedure | [14 empty] | 2018-02-12 | 2018-02-19
SDVC role/responsibility reassignment - PVC(E ) - editorial |  |  | SDVC | Academic | [15 empty] | 22/02/2018 PVC ( E) endorsed | 2018-02-23
Smoking Procedure - Major Review (to be renamed Smoke-Free Procedure) |  | Legal | DVC (ES) | Enterprise Services | University Procedure | [6 empty] | 27/3-11/4/18 | [5 empty] | 2018-04-18 |  | 2018-04-18 | 2018-05-30
Special Circumstances Procedure (Formerly Assessment of Compassionate & Compelling Circumstances) | Major Review |  | PVC (S) | Academic | University Procedure | Special Circumstances | [5 empty] | Review completed w/o Jan 18, pending some replies. |  | N/a | Jan 2021 | Jan 2021 | Feb 23 2021 | 2021-01-01 |  | VC | 2021-03-10
Standard Admissions Statements Schedule | Minor Review |  | DVC (A) | Academic | Schedule | USQ Upskill/Undergraduate Certificates | [13 empty] | DVC A | 2020-07-10
Student Academic Progress Procedure | Major Review |  | DVC (A) | Academic | University Procedure | Academic Standing, Progression and Exclusion | Q3 2021 |  |  |  |  | June 9 2021-June 10 2021 |  | N/A | [5 empty] | VC - Aug 8, 2021 | Oct 7, 2021 | ON HOLD for publication
Student Decision and Appeal Procedure | Development |  | DVC (A) | Academic | University Procedure | Student Grievance Resolution | Q4 2021 |  |  |  | Online consult closed, Jan 29 | Early March | Legal Check |  |  | May 6 | June 8 |  | July 29 | Aug 23 | Nov 12,2021
Student Grievance Resolution Policy | Development |  | VC | Vice-Chancellor | Governance Policy | Student Grievance Resolution | Q4 2021 |  |  |  | Online consult closed, Jan 29 | Feb 15 - But future review with procedures to be completed. | Legal Check | Exemption: June 2, 2021 |  | May 6 | June 8 |  | July 29 | Aug 23 | Nov 12,2021 | Committee Based Student Appeals Procedure? eb: Leanne processing feedback, working on procedures, collecting consultation. Went to Chancellor's in May with proposal to make this Academic Quality with repeal of existing Governance policy but Chancellor's wants to keep it Governance. Mar: Still on track for May. Back to Chancellor's Committee in May.
Student Grievance Resolution Procedure | Development |  | DVC (A) | Academic | University Procedure | Student Grievance Resolution | Q4 2021 |  |  |  | Online consult closed, Jan 29 | Early March | Legal Check |  |  | May 6 | June 8 |  | July 29 | Aug 23 | Nov 12, 2021
USQ UpSkill policy alignment suite (Note 7) |  | Legal | VC | Vice-Chancellor | Governance Policy, 2 x University Procedure | [5 empty] | UpSkill Gov Group 31/3/19 |  |  | ED (CMS) exemption 30/1/19 |  | n/a | 19/02/2019 (noting) | noting only post VC approval | n/a | VC 12/2/19 | 2019-03-11
Various - Academic Freedom Alignment Changes - Editorial | Alignment | Compliance | VC | Academic | Various | Academic Freedom Alignment Changes | Q2 2021 | [13 empty] | 2021-06-04
Various - Human Rights Amendments | Alignment | Compliance | CPO | Enterprise Services | Various | International Sanctions | Q4-Q1 2022 | [13 empty] | 2020-10-09
Work Health and Safety Procedures and Safety Manuals Procedure | Minor Review |  | DVC (ES) | Enterprise Services | University Procedure | WH&S | Q2 2021 | [13 empty] | 2021-05-21
Working with Children Procedure | Minor Review | Compliance | CPO | Enterprise Services | University Procedure | Working with Children | [14 empty] | 2020-10-09
Workplace Adjustments (Major Review) |  |  | CPO | Enterprise Services | University Procedure | [6 empty] | Feb 17, 2020 Completed 1. Review & Consideration. |  | N/A |  |  |  | June 24, 2020 |  |  | 2020-06-26
Unreasonable Complainant Conduct - Students Procedure | Development | Audit, Compliance | Provost | Vice-Chancellor | Executive Policy | Complaints (Institutional) | Q4-Q1 2023 | [5 empty] | Legal Request | [7 empty] | 2023-03-01
Complaints Management Procedure | Development | Audit, Compliance | Provost | Vice-Chancellor | Executive Policy | Complaints (Institutional) | Q4-Q1 2023 | [5 empty] | Legal Request | [7 empty] | 2023-03-01
Complaint Management Policy | Development | Audit, Compliance | Provost | Vice-Chancellor | Executive Policy | Complaints (Institutional) | Q4-Q1 2023 | [5 empty] | Legal Request | [7 empty] | 2023-03-01 | Shared at PIT Feb 2021 - concept is "catch-all" to cover where other procedures/policies don't. Les still wants to move this forward, but waiting to see how the Student Grievance Resolution Policy/Procedure goes. Currently being worked on by Grievance Resolution unit. Handed over from Les Mitchell to Academic Policy Team
Course Nomenclature and Coding Schedule | Major Review |  | Provost | Academic | University Procedure |  | Q1 - Q2 2023 | [13 empty] | 2022-12-01 | Implementation for January 2023
Student General Conduct Policy | Major Review |  | Provost | Vice-Chancellor | Governance Policy | Student Conduct | Q1-Q2 2023 | [5 empty] | Legal Request | [7 empty] | 2022-12-01 | There is a specific working group for this, and it is a "Student Lead" group. Get some early legal feedback, now with Linda Bird for feedback.
Learning and Teaching Policy | Major Review |  | Provost | Academic | Academic Quality Policy | Learning and Teaching | Q4 2022 |  |  |  | Currently under consultation | [9 empty] | 2022-12-01 | Per CS as of Feb 28 - she has no idea what is happening with this one. Dropped with departure of PVC (E), pushed back to 2021. (March 2020). June 2021: what is status? What is timing?
Articulation Arrangements Procedure | Development |  | Provost | Academic | University Procedure | Education Partnerships | Q1-Q2 2023 - May not go ahead |  |  |  |  | Oct/Nov' est. | Legal Request |  |  | Jan 2021 | Feb 2021 | Jan/Feb 2021 |  | VC Feb 2021 | 2022-06-01 | 24 June Consultation; Remaining procedures Stage 5, estimate timing: Late February (Articulation Arrangements); Dual & Collaborative - Later, though Collaborative may not go ahead. Feb: Getting MAPSEM feedback late Feb on Articulation Arrangements. So Stage 5 likely in March. Dual/Joint - pending update/timing. June 2021: Earliest date for Approval Sept Key Contact: Leanne Mar: No update from Leanne. May: MAPSEM feedback on articulation came back. Endorsed by AB subject o legal review, still sitting there.
Course Management, Approval, Change and Discontinuation Procedure (Course Management) | Development |  | Provost | Academic | University Procedure | Academic Programs and Courses | Q4 2022 | [13 empty] | 2023-12-01
Art Collection Procedure | Development |  | PVC (Eng) | Vice-Chancellor | University Procedure | Art Collection | Q2-Q3 2022 | [13 empty] | 2022-10-01
Artifical Intelligence (Ethical Application) | Development |  | VC | Vice-Chancellor | Governance Policy | Artifical Intelligence/Data Ethics | Q2-Q3 2022 | [13 empty] | 2022-10-01 | Policy 101 with Jamil Oct 8, 2021
Art Collection Policy | Development |  | PVC (Eng) | Vice-Chancellor | Executive Policy | Art Collection | Q1-Q2 2022 | [13 empty] | 2022-10-01 | Went to VCE but knocked back with "Do we need this as a Policy"? Per Brodei Taylor, intend to resubmit with greater rationale.
Student Advice, Student Wellfare and Pastoral Support Policy and Procedure | Repeal |  | Provost | Academic |  |  | Q3 - Q4 2023
Student Authority to Act Procedure | Major Review |  | Dir (SAS) | Academic |  |  | Q4 2023
Student Authority to Act Schedule | Minor Review |  | Dir (SAS) | Academic |  |  | Q4 2023
Handling Student Information Policy and Procedure | Repeal |  | Provost | Academic |  |  | Q1 - Q2 2024 | Possible Repeal
Coursework Quality Assurance – Evaluation Procedure | Major Review |  | Provost | Academic |  |  | Q3 2023
Equity in Education Policy and Procedure | Repeal |  | Provost | Academic |  |  | Q3 - Q4 2023
Program Nomenclature Schedule | Major Review |  | Provost | Academic |  |  | Q3 2023 | [13 empty] | 2023-08-01
Program Quality Assurance and Re-accreditation Procedure | Major Review |  | Provost | Academic |  |  | Q3 2023 | [13 empty] | 2023-08-01
Religious Services Policy and Procedure | Repeal |  | Provost | Academic |  |  | Q3 - Q4 2023 | [13 empty] | 2023-07-24
Multiculturalism Policy and Procedure | Repeal |  | Provost | Academic |  |  | Q3 - Q4 2023 | [13 empty] | 2023-07-24
Access to the Student Record Base Policy and Procedure | Repeal |  | Provost | Academic |  |  | Q3 - Q4 2023 | [13 empty] | 2023-07-24
Professional Accreditation Schedule | Repeal |  | Provost | Academic | Schedule | Professional Accreditation | Q2 2023 | Possibly just a list | [12 empty] | 2023-07-24 | Dependant on roll out of new CMS
Standard Admissions Statements Schedule | Repeal |  | Provost | Academic
Academic Integrity Policy | Major Review |  | Provost | Academic
Academic Integrity Procedure | Major Review |  | Provost | Academic
Sponsorships Policy | Development |  | PVC (ENG) | Vice-Chancellor | Executive Policy | Sponsorships | ON HOLD |  |  |  |  | Review: Sept 18-Sept 25; Consideration: Sept 25+ | Legal Request | Nov 9-21 |  |  |  | Jan 20, 2021 - Further Revision and subsequent VCE required. |  |  | 2022-12-01 | Placed on hold pending Audit and potentially revised framework with new PVC (Eng)
Media Engagement Policy | Major Review |  | PVC (ENG) |  |  |  | TBA | Following up on status
Media Engagemenr Procedure | Major Review |  | PVC (ENG) |  |  |  | TBA | Following up on status
Official Information Policy and Procedure | Major Review |  | pvc (eng) |  |  |  | TBA | Following up on status
View
PDF EXPORT
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
Note on S172: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Requires parallel path with gazettal
Note on S205: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Requires parallel path with gazettal
Note on S207: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Requires parallel path with gazettal

## Preliminary Notes (hidden)
Preliminary Notes (Table only viewable by the Policy Advisor)
Division | Topic | Notes
Academic | Academic Transformation Implementation | Helen Drury rang July 6 re: disbanding of OLAT. She'll talk to Leanne and will likely come back with request to do contextual search so we can do a mass search/replace.

## Policy Activity Report (hidden)
Total Instruments
190
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Policy Activity Table (hidden)
Count of Report State | Column Labels
Row Labels | Alignment | Development | Major Review | Minor Review | Repeal | Grand Total
(blank) |  | 1 |  | 1 |  | 2
CFO | 1 | 3 | 18 | 7 |  | 29
CPO | 1 | 2 | 5 | 2 | 3 | 13
Dir (AS) | 2 |  |  |  |  | 2
Dir (I&PC) |  |  |  | 1 |  | 1
Dir (SAS) |  |  | 3 | 1 |  | 4
DVC (AA) |  |  | 1 |  |  | 1
DVC (ES) |  | 21 | 11 | 1 |  | 33
DVC (R&I) | 2 | 6 | 6 |  |  | 14
ED (FM) |  | 14 | 5 |  |  | 19
ED (ICT) |  |  | 2 |  |  | 2
Privacy Officer |  | 1 | 3 |  |  | 4
Provost |  | 14 | 16 |  | 10 | 40
PVC (Eng) |  | 4 | 3 |  |  | 7
TBD |  |  | 1 |  |  | 1
VC | 1 | 7 | 6 | 4 |  | 18
Grand Total | 7 | 73 | 80 | 17 | 13 | 190

## Data Validation (hidden)
Accountable Officer (Abbrv) | Degree of Change | Policy Type | Priority Status | Progress Stage | Top 3 Priority | Key Drivers | USQ Priorities | Division | Legal Check
CFO | Alignment | Academic Quality Policy | Development (new) | 1. Confirm Requirement | Top 3 Priority | Regulatory | TBA | Academic | Team Request
Chancellor | Development | Executive Policy | Proposed Repeal | 2. Research |  | Strategic |  | Enterprise Services | Legal Request
CPO | Major Review | Governance Policy | Residual Priority (previous year) | 3. Initial Draft |  | Audit |  | Research | SI Advised
Dean (GRS) | Minor Review | Policy Library Resource | Scheduled Review | 4. Preliminary Consultation |  | Change |  | Vice-Chancellor
Dir (AS) | Repeal | Schedule | Unscheduled Review | 5. Review |  | Other
Dir (I&PC) |  | University Procedure |  | 6. Consultation
Dir (LS) |  | Various |  | 7. Revise Draft
Dir (PPSS) |  |  |  | 8. Endorsement
Dir (SAS) |  |  |  | 9. Approval
DVC (AA) |  |  |  | 10. Publication
DVC (ES) |  |  |  | 11. Communication
DVC (R&I) |  |  |  | 12. Implementation
ED (FM)
ED (ICT)
Privacy Officer
Provost
PVC (E)
PVC (ENG)
PVC (S)
TBD
Uni Secretary
VC

## Key & Issues Notes (hidden)
Key
CI Project
Active
Completed
Published
Issues / Notes
Note 1